## Project_Overview
ProjectID | ProjectName | DatasetSet | ProjectTheme | Sponsor | ProjectManager | Portfolio | Domain | DeliveryMethod | StartDate | EndDate | CurrentPhase | HealthRAG | Complexity | RiskProfile | Maturity | Description
PRJ-A-001 | Starfleet DevEx Portal | SetA | Star Trek | Geordi La Forge | Data | Digital Delivery | Web Platform | Agile | 2027-01-01 | 2027-06-11 | Discovery | Green | Low | Low | Emerging | Starfleet DevEx Portal delivering Web Platform capabilities using Agile methods within the Star Trek universe.

## Resources
ResourceID | ResourceName | Role | SkillTier | Location | CostRate_USD_per_hour | BillRate_USD_per_hour | UtilizationTarget_pct | AllocationStart | AllocationEnd
R-A-001 | Worf | Data Engineer | Senior | Star Trek – Remote | 129.37 | 187.86 | 88.1 | 2027-01-02 | 2027-02-24
R-A-002 | Chekov | Data Engineer | Senior | Star Trek – Remote | 123.82 | 163.44 | 81 | 2027-04-08 | 2027-02-08
R-A-003 | James T. Kirk | Developer | Junior | Star Trek – Remote | 97.52 | 133.51 | 87.3 | 2027-05-18 | 2027-02-15
R-A-004 | James T. Kirk (3) | Data Engineer | Senior | Star Trek – Remote | 138.64 | 225.04 | 85.8 | 2027-01-18 | 2027-01-26
R-A-005 | Spock | Architect | Mid | Star Trek – Remote | 199.58 | 337.96 | 88.7 | 2027-04-08 | 2027-03-27
R-A-006 | Uhura | QA Engineer | Senior | Star Trek – Remote | 110.05 | 145.62 | 82.1 | 2027-03-10 | 2027-02-02
R-A-007 | Uhura (6) | UX Designer | Mid | Star Trek – Remote | 90.27 | 142.46 | 84.6 | 2027-03-11 | 2027-06-06
R-A-008 | Data | Developer | Junior | Star Trek – Remote | 95.94 | 153.1 | 82.3 | 2027-01-09 | 2027-04-05
R-A-009 | Worf (8) | Developer | Senior | Star Trek – Remote | 75.3 | 125.07 | 82.1 | 2027-05-08 | 2027-04-26
R-A-010 | James T. Kirk (9) | DevOps Engineer | Mid | Star Trek – Remote | 145 | 190.57 | 82.5 | 2027-05-24 | 2027-06-01
R-A-011 | Data (10) | Developer | Principal | Star Trek – Remote | 116.77 | 193.14 | 83.6 | 2027-02-05 | 2027-05-25
R-A-012 | Uhura (11) | QA Engineer | Mid | Star Trek – Remote | 105.35 | 172.51 | 86.3 | 2027-04-19 | 2027-01-31
R-A-013 | Geordi La Forge | Developer | Senior | Star Trek – Remote | 117.67 | 171.87 | 89.7 | 2027-01-03 | 2027-02-13
R-A-014 | Beverly Crusher | Data Engineer | Senior | Star Trek – Remote | 137.59 | 188.51 | 81.1 | 2027-04-22 | 2027-02-24

## Capacity_Effort
Month | ResourceID | Role | CapacityHours | PlannedHours | ActualHours | VarianceHours | Utilization_pct
2027-01-01 | R-A-001 | Data Engineer | 160 | 140.3 | 150.9 | 10.5 | 94.3
2027-01-01 | R-A-004 | Data Engineer | 56 | 46.9 | 43.9 | -3 | 78.4
2027-01-01 | R-A-008 | Developer | 120 | 102.8 | 98.7 | -4.1 | 82.2
2027-01-01 | R-A-013 | Developer | 160 | 145.5 | 135.4 | -10.1 | 84.6
2027-02-01 | R-A-001 | Data Engineer | 144 | 130.2 | 137.4 | 7.3 | 95.5
2027-02-01 | R-A-008 | Developer | 160 | 132.1
2027-02-01 | R-A-011 | Developer | 128 | 105.1
2027-02-01 | R-A-013 | Developer | 80 | 74.8 | 79.8 | 5 | 99.8
2027-03-01 | R-A-007 | UX Designer | 120 | 99.6 | 107.1 | 7.5 | 89.2
2027-03-01 | R-A-008 | Developer | 184 | 158.2 | 157.8 | -0.4 | 85.7
2027-03-01 | R-A-011 | Developer | 184 | 147.2 | 155 | 7.8 | 84.3
2027-04-01 | R-A-007 | UX Designer | 176 | 143.4 | 144.8 | 1.4 | 82.3
2027-04-01 | R-A-008 | Developer | 24 | 19.3 | 19 | -0.3 | 79.1
2027-04-01 | R-A-011 | Developer | 176 | 142.9 | 149.5 | 6.6 | 84.9
2027-05-01 | R-A-007 | UX Designer | 168 | 137.9 | 151.5 | 13.7 | 90.2
2027-05-01 | R-A-010 | DevOps Engineer | 48 | 40.2 | 40.3 | 0.1 | 84
2027-05-01 | R-A-011 | Developer | 136 | 109.4 | 105.8 | -3.5 | 77.8
2027-06-01 | R-A-007 | UX Designer | 32 | 27.3 | 25.8 | -1.5 | 80.6
2027-06-01 | R-A-010 | DevOps Engineer | 8 | 6.3 | 6 | -0.3 | 74.7

## Budget_Costs
Month | CostCategory | PlannedCost_USD | ActualCost_USD | ForecastCost_USD | CumPlanned_USD | CumActual_USD | CumForecast_USD | EV | PV | AC | CPI | SPI
2027-01-01 | Labor | 51636.44 | 51010.03 | 49194.44 | 71992.66 | 71313.07 | 72093.47 | 5353.04 | 71992.66 | 71313.07 | 0.075 | 0.074
2027-01-01 | Software | 7257.09 | 7217.42 | 7183.42 | 71992.66 | 71313.07 | 72093.47 | 5353.04 | 71992.66 | 71313.07 | 0.075 | 0.074
2027-01-01 | Infra | 9240.1 | 9766.08 | 9482.66 | 71992.66 | 71313.07 | 72093.47 | 5353.04 | 71992.66 | 71313.07 | 0.075 | 0.074
2027-01-01 | Travel | 662.72 | 703.47 | 684.91 | 71992.66 | 71313.07 | 72093.47 | 5353.04 | 71992.66 | 71313.07 | 0.075 | 0.074
2027-01-01 | Contingency | 3196.31 | 2998.4 | 3148.06 | 71992.66 | 71313.07 | 72093.47 | 5353.04 | 71992.66 | 71313.07 | 0.075 | 0.074
2027-02-01 | Labor | 50591.89 | 53739.52 | 52744.58 | 137098.89 | 138982.88 | 137261.98 | 32742.46 | 137098.89 | 138982.88 | 0.236 | 0.239
2027-02-01 | Software | 3027.51 | 2876.02 | 2804.64 | 137098.89 | 138982.88 | 137261.98 | 32742.46 | 137098.89 | 138982.88 | 0.236 | 0.239
2027-02-01 | Infra | 5585 | 6057.79 | 6161.69 | 137098.89 | 138982.88 | 137261.98 | 32742.46 | 137098.89 | 138982.88 | 0.236 | 0.239
2027-02-01 | Travel | 1192.56 | 1178.99 | 1224.22 | 137098.89 | 138982.88 | 137261.98 | 32742.46 | 137098.89 | 138982.88 | 0.236 | 0.239
2027-02-01 | Contingency | 4709.28 | 5049.62 | 5143.92 | 137098.89 | 138982.88 | 137261.98 | 32742.46 | 137098.89 | 138982.88 | 0.236 | 0.239
2027-03-01 | Labor | 41357.14 | 42906.6 | 44220.67 | 195448.68 | 198264.11 | 199029.52 | 137070.28 | 195448.68 | 198264.11 | 0.691 | 0.701
2027-03-01 | Software | 5899.05 | 5622.03 | 6016.85 | 195448.68 | 198264.11 | 199029.52 | 137070.28 | 195448.68 | 198264.11 | 0.691 | 0.701
2027-03-01 | Infra | 7332.8 | 7749.41 | 7625.05 | 195448.68 | 198264.11 | 199029.52 | 137070.28 | 195448.68 | 198264.11 | 0.691 | 0.701
2027-03-01 | Travel | 688.7 | 682.5 | 699.94 | 195448.68 | 198264.11 | 199029.52 | 137070.28 | 195448.68 | 198264.11 | 0.691 | 0.701
2027-03-01 | Contingency | 3072.09 | 3024.79 | 2938.64 | 195448.68 | 198264.11 | 199029.52 | 137070.28 | 195448.68 | 198264.11 | 0.691 | 0.701
2027-04-01 | Labor | 31482.79 | 32351.07 | 32307.91 | 239060.35 | 242342.84 | 244469.58 | 241251.44 | 239060.35 | 242342.84 | 0.995 | 1.009
2027-04-01 | Software | 2508.26 | 2336.41 | 2447.29 | 239060.35 | 242342.84 | 244469.58 | 241251.44 | 239060.35 | 242342.84 | 0.995 | 1.009
2027-04-01 | Infra | 6148.79 | 6715.44 | 6316.96 | 239060.35 | 242342.84 | 244469.58 | 241251.44 | 239060.35 | 242342.84 | 0.995 | 1.009
2027-04-01 | Travel | 1044.2 | 956.51 | 953.89 | 239060.35 | 242342.84 | 244469.58 | 241251.44 | 239060.35 | 242342.84 | 0.995 | 1.009
2027-04-01 | Contingency | 2427.63 | 2275.09 | 2427.28 | 239060.35 | 242342.84 | 244469.58 | 241251.44 | 239060.35 | 242342.84 | 0.995 | 1.009
2027-05-01 | Labor | 31051.87 | 31873.67 | 30965.08 | 280034.4 | 284160.72 | 286846.7 | 281467.05 | 280034.4 | 284160.72 | 0.991 | 1.005
2027-05-01 | Software | 2317.14 | 2196.04 | 2301.01 | 280034.4 | 284160.72 | 286846.7 | 281467.05 | 280034.4 | 284160.72 | 0.991 | 1.005
2027-05-01 | Infra | 4321.73 | 4231.66 | 4085.26 | 280034.4 | 284160.72 | 286846.7 | 281467.05 | 280034.4 | 284160.72 | 0.991 | 1.005
2027-05-01 | Travel | 1079.84 | 1116.92 | 1097.49 | 280034.4 | 284160.72 | 286846.7 | 281467.05 | 280034.4 | 284160.72 | 0.991 | 1.005
2027-05-01 | Contingency | 2203.48 | 2115.34 | 2257.79 | 280034.4 | 284160.72 | 286846.7 | 281467.05 | 280034.4 | 284160.72 | 0.991 | 1.005
2027-06-01 | Labor | 3377.87 | 3198.97 | 3320.89 | 284399.91 | 288405.98 | 290993.12 | 277925.5 | 284399.91 | 288405.98 | 0.964 | 0.977
2027-06-01 | Software | 505.36 | 539.09 | 499.73 | 284399.91 | 288405.98 | 290993.12 | 277925.5 | 284399.91 | 288405.98 | 0.964 | 0.977
2027-06-01 | Infra | 206.01 | 214.4 | 217.74 | 284399.91 | 288405.98 | 290993.12 | 277925.5 | 284399.91 | 288405.98 | 0.964 | 0.977
2027-06-01 | Travel | 62.58 | 63.98 | 62.15 | 284399.91 | 288405.98 | 290993.12 | 277925.5 | 284399.91 | 288405.98 | 0.964 | 0.977
2027-06-01 | Contingency | 213.68 | 234.51 | 229.87 | 284399.91 | 288405.98 | 290993.12 | 277925.5 | 284399.91 | 288405.98 | 0.964 | 0.977

## Milestones
MilestoneID | MilestoneName | PlannedDate | ActualDate | Status | SlippageDays | Owner | Critical
MS-001 | MVP Build | 2027-01-11 | 2027-01-11 | Not Started | 0 | James T. Kirk (3) | FALSE
MS-002 | Training Complete | 2027-01-21 | 2027-01-20 | Not Started | -1 | Beverly Crusher | TRUE
MS-003 | Hypercare Complete | 2027-01-31 | 2027-01-30 | Not Started | -1 | Worf | TRUE
MS-004 | Security Assessment | 2027-02-10 | 2027-02-09 | Not Started | -1 | James T. Kirk | FALSE
MS-005 | Go-Live | 2027-02-20 | 2027-02-23 | Not Started | 3 | Worf | TRUE
MS-006 | Performance Test | 2027-03-02 | 2027-03-05 | Not Started | 3 | Worf | FALSE
MS-007 | System Integration | 2027-03-12 | 2027-03-13 | Not Started | 1 | James T. Kirk | TRUE
MS-008 | System Integration | 2027-03-22 | 2027-03-29 | Not Started | 7 | Beverly Crusher | TRUE
MS-009 | Hypercare Complete | 2027-04-01 | 2027-03-30 | Not Started | -2 | Data (10) | TRUE
MS-010 | Go-Live | 2027-04-11 | 2027-04-19 | Not Started | 8 | Uhura (6) | FALSE
MS-011 | Hypercare Complete | 2027-04-21 | 2027-04-19 | Not Started | -2 | Beverly Crusher | TRUE
MS-012 | System Integration | 2027-05-01 | 2027-05-02 | Not Started | 1 | Worf | TRUE
MS-013 | Go-Live | 2027-05-11 | 2027-05-12 | Not Started | 1 | Geordi La Forge | FALSE
MS-014 | Requirements Baseline | 2027-05-21 | 2027-05-20 | Not Started | -1 | James T. Kirk | FALSE
MS-015 | Design Complete | 2027-05-31 | 2027-05-26 | Not Started | -5 | Beverly Crusher | FALSE

## Risks_Issues_Dependencies
RID_ID | Type | Title | Description | Owner | ImpactArea | Probability_pct | Impact | Severity | ExposureScore | Status | TargetDate | Linkage
RID-001 | Risk | Risk #1 | Synthetic risk description for test purposes. | Beverly Crusher | Scope | 8 | Medium |  | 16 | Open | 2027-02-26 | Vendor-Contract
RID-002 | Dependency | Dependency #2 | Synthetic dependency description for test purposes. | Spock | Scope |  | Low |  |  | Open | 2027-05-25 | MS-001
RID-003 | Dependency | Dependency #3 | Synthetic dependency description for test purposes. | Spock | Quality |  | Low |  |  | Open | 2027-03-16 | Data-Center
RID-004 | Risk | Risk #4 | Synthetic risk description for test purposes. | Geordi La Forge | Cost | 70 | Low |  | 70 | Open | 2027-02-06 | Data-Center
RID-005 | Risk | Risk #5 | Synthetic risk description for test purposes. | Uhura (11) | Security | 73 | Medium |  | 146 | Open | 2027-02-27 | MS-001
RID-006 | Dependency | Dependency #6 | Synthetic dependency description for test purposes. | James T. Kirk (9) | Schedule |  | Low |  |  | Mitigated | 2027-03-25 | External-API
RID-007 | Risk | Risk #7 | Synthetic risk description for test purposes. | Spock | Quality | 53 | Medium |  | 106 | Mitigated | 2027-02-21 | Vendor-Contract
RID-008 | Issue | Issue #8 | Synthetic issue description for test purposes. | Worf | Quality |  | Low | Low |  | Mitigated | 2027-06-05 | Vendor-Contract
RID-009 | Risk | Risk #9 | Synthetic risk description for test purposes. | Data (10) | Schedule | 26 | Low |  | 26 | Open | 2027-01-29 | Data-Center
RID-010 | Risk | Risk #10 | Synthetic risk description for test purposes. | Geordi La Forge | Quality | 30 | Low |  | 30 | Open | 2027-02-14 | MS-005
RID-011 | Issue | Issue #11 | Synthetic issue description for test purposes. | Geordi La Forge | Quality |  | Low | Medium |  | Open | 2027-06-04 | External-API
RID-012 | Risk | Risk #12 | Synthetic risk description for test purposes. | James T. Kirk | Quality | 18 | Medium |  | 36 | Open | 2027-04-26 | Data-Center
RID-013 | Risk | Risk #13 | Synthetic risk description for test purposes. | James T. Kirk (3) | People | 22 | High |  | 66 | Closed | 2027-05-06 | Data-Center
RID-014 | Risk | Risk #14 | Synthetic risk description for test purposes. | Geordi La Forge | Quality | 69 | High |  | 207 | Closed | 2027-04-27 | Data-Center
RID-015 | Dependency | Dependency #15 | Synthetic dependency description for test purposes. | Uhura (11) | People |  | High |  |  | Closed | 2027-03-12 | Vendor-Contract
RID-016 | Risk | Risk #16 | Synthetic risk description for test purposes. | James T. Kirk (3) | People | 41 | Low |  | 41 | Open | 2027-03-09 | Vendor-Contract
RID-017 | Risk | Risk #17 | Synthetic risk description for test purposes. | James T. Kirk | People | 32 | Low |  | 32 | Mitigated | 2027-01-24 | Vendor-Contract

## Operational_KPIs
WeekStart | KPI | PlannedValue | ActualValue | Unit | Notes
2026-12-28 | Build Velocity | 38.64 | 35.25 | points
2026-12-28 | Defect Leakage | 10.33 | 8.38 | defects
2026-12-28 | Cycle Time | 6.85 | 8.03 | days
2026-12-28 | MTTR | 4.16 | 5.06 | hours
2027-01-04 | Build Velocity | 43.03 | 42.83 | points
2027-01-04 | Defect Leakage | 11.43 | 8.44 | defects
2027-01-04 | Cycle Time | 4.95 | 5.67 | days
2027-01-04 | MTTR | 10.69 | 10.44 | hours
2027-01-11 | Build Velocity | 49.39 | 52.35 | points
2027-01-11 | Defect Leakage | 10.98 | 9.78 | defects
2027-01-11 | Cycle Time | 4.36 | 4.12 | days
2027-01-11 | MTTR | 7.11 | 7.6 | hours
2027-01-18 | Build Velocity | 51.93 | 54.25 | points
2027-01-18 | Defect Leakage | 10.41 | 12.86 | defects
2027-01-18 | Cycle Time | 7.9 | 7.64 | days
2027-01-18 | MTTR | 11.26 | 11.42 | hours
2027-01-25 | Build Velocity | 46.52 | 42.65 | points
2027-01-25 | Defect Leakage | 6.29 | 7.5 | defects
2027-01-25 | Cycle Time | 3.91 | 3.24 | days
2027-01-25 | MTTR | 6.62 | 6.08 | hours
2027-02-01 | Build Velocity | 33.5 | 36.04 | points
2027-02-01 | Defect Leakage | 4.78 | 6.03 | defects
2027-02-01 | Cycle Time | 5.11 | 5.71 | days
2027-02-01 | MTTR | 7.76 | 8.73 | hours
2027-02-08 | Build Velocity | 22.08 | 24.08 | points
2027-02-08 | Defect Leakage | 4.24 | 2.35 | defects
2027-02-08 | Cycle Time | 7.79 | 5.61 | days
2027-02-08 | MTTR | 4.25 | 3.28 | hours
2027-02-15 | Build Velocity | 53.57 | 54.87 | points
2027-02-15 | Defect Leakage | 4.39 | 3.85 | defects
2027-02-15 | Cycle Time | 3.57 | 4.19 | days
2027-02-15 | MTTR | 7.72 | 6.02 | hours
2027-02-22 | Build Velocity | 34.76 | 35.49 | points
2027-02-22 | Defect Leakage | 11.64 | 12.51 | defects
2027-02-22 | Cycle Time | 6.89 | 5.39 | days
2027-02-22 | MTTR | 6.49 | 6.52 | hours
2027-03-01 | Build Velocity | 57.16 | 58.02 | points
2027-03-01 | Defect Leakage | 11.08 | 8.87 | defects
2027-03-01 | Cycle Time | 7.71 | 6.16 | days
2027-03-01 | MTTR | 8.74 | 10.32 | hours
2027-03-08 | Build Velocity | 29.71 | 30.89 | points
2027-03-08 | Defect Leakage | 5.02 | 5.25 | defects
2027-03-08 | Cycle Time | 7.03 | 7.72 | days
2027-03-08 | MTTR | 8.53 | 5.36 | hours
2027-03-15 | Build Velocity | 41.31 | 42.64 | points
2027-03-15 | Defect Leakage | 2.69 | 2.74 | defects
2027-03-15 | Cycle Time | 3.06 | 2.79 | days
2027-03-15 | MTTR | 7.92 | 7.16 | hours
2027-03-22 | Build Velocity | 34.49 | 37.19 | points
2027-03-22 | Defect Leakage | 6.6 | 4.11 | defects
2027-03-22 | Cycle Time | 3.88 | 3.73 | days
2027-03-22 | MTTR | 9.2 | 9.49 | hours
2027-03-29 | Build Velocity | 56.78 | 59.9 | points
2027-03-29 | Defect Leakage | 6.65 | 7.72 | defects
2027-03-29 | Cycle Time | 5.96 | 5.13 | days
2027-03-29 | MTTR | 5.96 | 7.48 | hours
2027-04-05 | Build Velocity | 31.16 | 30.85 | points
2027-04-05 | Defect Leakage | 9.5 | 9.09 | defects
2027-04-05 | Cycle Time | 6.34 | 5.51 | days
2027-04-05 | MTTR | 7.95 | 6.58 | hours
2027-04-12 | Build Velocity | 39.5 | 38.36 | points
2027-04-12 | Defect Leakage | 4.58 | 3.32 | defects
2027-04-12 | Cycle Time | 5.98 | 6.82 | days
2027-04-12 | MTTR | 8.45 | 8.12 | hours
2027-04-19 | Build Velocity | 27.64 | 26.21 | points
2027-04-19 | Defect Leakage | 6.06 | 5.73 | defects
2027-04-19 | Cycle Time | 4.2 | 3.94 | days
2027-04-19 | MTTR | 9.69 | 8.86 | hours
2027-04-26 | Build Velocity | 20.69 | 19.84 | points
2027-04-26 | Defect Leakage | 6.04 | 4.2 | defects
2027-04-26 | Cycle Time | 6.32 | 5.59 | days
2027-04-26 | MTTR | 8.43 | 7.08 | hours
2027-05-03 | Build Velocity | 59.87 | 60.47 | points
2027-05-03 | Defect Leakage | 5.52 | 4.76 | defects
2027-05-03 | Cycle Time | 4.53 | 3.7 | days
2027-05-03 | MTTR | 9.77 | 8.02 | hours
2027-05-10 | Build Velocity | 49.72 | 54.2 | points
2027-05-10 | Defect Leakage | 8.9 | 5.81 | defects
2027-05-10 | Cycle Time | 6.69 | 5.61 | days
2027-05-10 | MTTR | 8.72 | 9.87 | hours
2027-05-17 | Build Velocity | 43.87 | 48.09 | points
2027-05-17 | Defect Leakage | 10.33 | 7.61 | defects
2027-05-17 | Cycle Time | 4.8 | 4.09 | days
2027-05-17 | MTTR | 9.66 | 6.65 | hours
2027-05-24 | Build Velocity | 21.82 | 19.88 | points
2027-05-24 | Defect Leakage | 4.92 | 6.18 | defects
2027-05-24 | Cycle Time | 6.19 | 6.66 | days
2027-05-24 | MTTR | 4.82 | 2.93 | hours
2027-05-31 | Build Velocity | 31.37 | 31.24 | points
2027-05-31 | Defect Leakage | 5.41 | 6.88 | defects
2027-05-31 | Cycle Time | 4.26 | 4.82 | days
2027-05-31 | MTTR | 4.91 | 3.17 | hours
2027-06-07 | Build Velocity | 39.67 | 40.28 | points
2027-06-07 | Defect Leakage | 8.86 | 5.51 | defects
2027-06-07 | Cycle Time | 7.06 | 8.29 | days
2027-06-07 | MTTR | 4.68 | 3.62 | hours

## Data_Dictionary
Sheet | Column | Description
Project_Overview | ProjectID | Global unique project ID
Project_Overview | ProjectName | Fictional project name
Project_Overview | DatasetSet | SetA/SetB/SetC
Project_Overview | ProjectTheme | Fictional universe label
Project_Overview | Sponsor | Fictional sponsor
Project_Overview | ProjectManager | Fictional PM
Project_Overview | Portfolio | Portfolio grouping
Project_Overview | Domain | Solution domain
Project_Overview | DeliveryMethod | Agile/Hybrid/Waterfall
Project_Overview | StartDate | Planned start date
Project_Overview | EndDate | Planned end date
Project_Overview | CurrentPhase | Current phase at time of generation
Project_Overview | HealthRAG | Red/Amber/Green overall health
Project_Overview | Complexity | Low/Medium/High
Project_Overview | RiskProfile | Low/Medium/High
Project_Overview | Maturity | Emerging/Defined/Optimized
Project_Overview | Description | Short description
Resources | ResourceID | Unique resource key
Resources | ResourceName | Fictional name
Resources | Role | Role on project
Resources | SkillTier | Junior/Mid/Senior/Principal
Resources | Location | Fictional/Generic location
Resources | CostRate_USD_per_hour | Internal cost rate ($/hr)
Resources | BillRate_USD_per_hour | External bill rate ($/hr)
Resources | UtilizationTarget_pct | Target utilization %
Resources | AllocationStart | Allocation start date
Resources | AllocationEnd | Allocation end date
Capacity_Effort | Month | First day of month
Capacity_Effort | ResourceID | FK to Resources
Capacity_Effort | Role | Role on project
Capacity_Effort | CapacityHours | Capacity hours in month
Capacity_Effort | PlannedHours | Planned hours
Capacity_Effort | ActualHours | Actual hours
Capacity_Effort | VarianceHours | Actual - Planned
Capacity_Effort | Utilization_pct | Actual/Capacity*100
Budget_Costs | Month | First day of month
Budget_Costs | CostCategory | Labor/Software/Infra/Travel/Contingency
Budget_Costs | PlannedCost_USD | Planned monthly cost
Budget_Costs | ActualCost_USD | Actual monthly cost
Budget_Costs | ForecastCost_USD | Forecast monthly cost
Budget_Costs | CumPlanned_USD | Cumulative planned cost
Budget_Costs | CumActual_USD | Cumulative actual cost
Budget_Costs | CumForecast_USD | Cumulative forecast cost
Budget_Costs | EV | Earned Value (cumulative)
Budget_Costs | PV | Planned Value (cumulative)
Budget_Costs | AC | Actual Cost (cumulative)
Budget_Costs | CPI | EV/AC
Budget_Costs | SPI | EV/PV
Milestones | MilestoneID | Unique milestone ID
Milestones | MilestoneName | Milestone title
Milestones | PlannedDate | Planned completion date
Milestones | ActualDate | Actual completion date (optional)
Milestones | Status | Status string
Milestones | SlippageDays | Actual - Planned (days)
Milestones | Owner | Responsible resource
Milestones | Critical | Critical path flag
Risks_Issues_Dependencies | RID_ID | Unique RID ID
Risks_Issues_Dependencies | Type | Risk/Issue/Dependency
Risks_Issues_Dependencies | Title | Short title
Risks_Issues_Dependencies | Description | Narrative description
Risks_Issues_Dependencies | Owner | Responsible resource
Risks_Issues_Dependencies | ImpactArea | Scope/Cost/Schedule/Quality/People/Security
Risks_Issues_Dependencies | Probability_pct | Probability for Risks (0-100%)
Risks_Issues_Dependencies | Impact | Impact level (Low/Medium/High)
Risks_Issues_Dependencies | Severity | Issue severity (Low/Medium/High)
Risks_Issues_Dependencies | ExposureScore | Risk exposure (prob*impact weight)
Risks_Issues_Dependencies | Status | Open/Mitigated/Closed/Transferred/Accepted
Risks_Issues_Dependencies | TargetDate | Target resolve date
Risks_Issues_Dependencies | Linkage | Related milestone/dependency
Operational_KPIs | WeekStart | Week start date (Monday)
Operational_KPIs | KPI | KPI name
Operational_KPIs | PlannedValue | Planned value
Operational_KPIs | ActualValue | Actual value
Operational_KPIs | Unit | Unit of measure
Operational_KPIs | Notes | Notes