## Project_Overview
ProjectID | ProjectName | DatasetSet | ProjectTheme | Sponsor | ProjectManager | Portfolio | Domain | DeliveryMethod | StartDate | EndDate | CurrentPhase | HealthRAG | Complexity | RiskProfile | Maturity | Description
PRJ-A-002 | Wakanda Analytics Lake | SetA | Marvel Black Panther | Zuri | Ayo | Digital Delivery | Data Platform | Hybrid | 2027-01-01 | 2027-11-05 | Discovery | Amber | Medium | Low | Defined | Wakanda Analytics Lake delivering Data Platform capabilities using Hybrid methods within the Marvel Black Panther universe.

## Resources
ResourceID | ResourceName | Role | SkillTier | Location | CostRate_USD_per_hour | BillRate_USD_per_hour | UtilizationTarget_pct | AllocationStart | AllocationEnd
R-A-001 | Jabari Elder | Developer | Principal | Marvel Black Panther – Remote | 88.52 | 138.81 | 80.7 | 2027-04-30 | 2027-05-30
R-A-002 | W'Kabi | Data Engineer | Mid | Marvel Black Panther – Remote | 143.75 | 222.46 | 84.3 | 2027-10-06 | 2027-05-10
R-A-003 | M'Baku | Architect | Junior | Marvel Black Panther – Remote | 211.76 | 343.47 | 80.6 | 2027-06-07 | 2027-11-02
R-A-004 | Jabari Elder (3) | DevOps Engineer | Senior | Marvel Black Panther – Remote | 130.74 | 191 | 87 | 2027-05-20 | 2027-09-28
R-A-005 | Jabari Elder (4) | QA Engineer | Principal | Marvel Black Panther – Remote | 86.27 | 131.05 | 87.3 | 2027-05-09 | 2027-01-28
R-A-006 | T'Challa | Business Analyst | Junior | Marvel Black Panther – Remote | 128.1 | 208.31 | 90 | 2027-05-18 | 2027-02-04
R-A-007 | Jabari Elder (6) | Data Engineer | Principal | Marvel Black Panther – Remote | 112.26 | 166.54 | 89.2 | 2027-04-03 | 2027-08-26
R-A-008 | Shuri | Architect | Senior | Marvel Black Panther – Remote | 174.26 | 224.98 | 84.1 | 2027-06-14 | 2027-03-09
R-A-009 | Nakia | DevOps Engineer | Senior | Marvel Black Panther – Remote | 123.09 | 192.29 | 86.6 | 2027-07-25 | 2027-10-23
R-A-010 | River Tribe Elder | Project Manager | Junior | Marvel Black Panther – Remote | 105.28 | 143.56 | 89.7 | 2027-07-26 | 2027-10-05
R-A-011 | Nakia (10) | DevOps Engineer | Principal | Marvel Black Panther – Remote | 100.08 | 164.25 | 84.1 | 2027-04-07 | 2027-10-07
R-A-012 | M'Baku (11) | Developer | Junior | Marvel Black Panther – Remote | 130.52 | 199.88 | 82 | 2027-10-09 | 2027-03-23
R-A-013 | River Tribe Elder (12) | Data Engineer | Mid | Marvel Black Panther – Remote | 148.88 | 194.24 | 87.1 | 2027-06-09 | 2027-10-24
R-A-014 | Shuri (13) | Project Manager | Junior | Marvel Black Panther – Remote | 124.48 | 168.19 | 84.6 | 2027-03-02 | 2027-04-03
R-A-015 | Okoye | QA Engineer | Senior | Marvel Black Panther – Remote | 103 | 152.34 | 84.2 | 2027-09-05 | 2027-09-13
R-A-016 | Nakia (15) | Developer | Mid | Marvel Black Panther – Remote | 114.1 | 162.32 | 88.6 | 2027-05-22 | 2027-08-15
R-A-017 | Okoye (16) | Developer | Junior | Marvel Black Panther – Remote | 133.02 | 182.27 | 82.8 | 2027-06-02 | 2027-09-22
R-A-018 | Ayo | DevOps Engineer | Senior | Marvel Black Panther – Remote | 131.26 | 192.68 | 85.5 | 2027-10-06 | 2027-07-27
R-A-019 | Shuri (18) | QA Engineer | Mid | Marvel Black Panther – Remote | 79.31 | 105.87 | 85.7 | 2027-04-30 | 2027-08-13
R-A-020 | Okoye (19) | Project Manager | Principal | Marvel Black Panther – Remote | 144.68 | 226.76 | 83.9 | 2027-03-19 | 2027-09-25
R-A-021 | T'Challa (20) | Data Engineer | Junior | Marvel Black Panther – Remote | 167.57 | 234.5 | 88.7 | 2027-08-14 | 2027-03-07
R-A-022 | W'Kabi (21) | QA Engineer | Principal | Marvel Black Panther – Remote | 87.42 | 137.7 | 88.7 | 2027-03-21 | 2027-02-22
R-A-023 | Zuri | QA Engineer | Principal | Marvel Black Panther – Remote | 118.15 | 165.69 | 86.5 | 2027-06-18 | 2027-10-15
R-A-024 | Jabari Elder (23) | Developer | Principal | Marvel Black Panther – Remote | 95.33 | 149.99 | 88.7 | 2027-01-19 | 2027-02-19
R-A-025 | Zuri (24) | Developer | Mid | Marvel Black Panther – Remote | 124.75 | 172.07 | 87.5 | 2027-08-11 | 2027-03-06

## Capacity_Effort
Month | ResourceID | Role | CapacityHours | PlannedHours | ActualHours | VarianceHours | Utilization_pct
2027-01-01 | R-A-024 | Developer | 72 | 65.5 | 60.3 | -5.2 | 83.7
2027-02-01 | R-A-024 | Developer | 120 | 102.9 | 93.2 | -9.7 | 77.7
2027-03-01 | R-A-014 | Project Manager | 176 | 146.3 | 142.1 | -4.1 | 80.8
2027-03-01 | R-A-020 | Project Manager | 72 | 60 | 58.9 | -1.1 | 81.9
2027-04-01 | R-A-001 | Developer | 8 | 6.6 | 6.1 | -0.4 | 76.8
2027-04-01 | R-A-007 | Data Engineer | 160 | 144.3 | 149.6 | 5.3 | 93.5
2027-04-01 | R-A-011 | DevOps Engineer | 144 | 121.1 | 114.6 | -6.5 | 79.6
2027-04-01 | R-A-014 | Project Manager | 16 | 13.7 | 14.2 | 0.5 | 88.6
2027-04-01 | R-A-019 | QA Engineer | 8 | 7.1 | 6.8 | -0.3 | 85.3
2027-04-01 | R-A-020 | Project Manager | 176 | 148.4 | 161.6 | 13.2 | 91.8
2027-05-01 | R-A-001 | Developer | 160 | 135.4 | 147.9 | 12.5 | 92.5
2027-05-01 | R-A-004 | DevOps Engineer | 64 | 56.7 | 54.5 | -2.2 | 85.1
2027-05-01 | R-A-007 | Data Engineer | 168 | 157.3 | 145 | -12.4 | 86.3
2027-05-01 | R-A-011 | DevOps Engineer | 168 | 139.6 | 133.9 | -5.7 | 79.7
2027-05-01 | R-A-016 | Developer | 48 | 43.4 | 46.2 | 2.9 | 96.3
2027-05-01 | R-A-019 | QA Engineer | 168 | 142.5
2027-05-01 | R-A-020 | Project Manager | 168 | 146.1 | 159.9 | 13.8 | 95.2
2027-06-01 | R-A-003 | Architect | 144 | 120.8 | 128.9 | 8 | 89.5
2027-06-01 | R-A-004 | DevOps Engineer | 176 | 159.3 | 150.7 | -8.6 | 85.6
2027-06-01 | R-A-007 | Data Engineer | 176 | 161.7 | 151.7 | -10 | 86.2
2027-06-01 | R-A-011 | DevOps Engineer | 176 | 144.3 | 152 | 7.7 | 86.4
2027-06-01 | R-A-013 | Data Engineer | 128 | 113.5 | 104.4 | -9.1 | 81.5
2027-06-01 | R-A-016 | Developer | 176 | 157.9 | 167 | 9.1 | 94.9
2027-06-01 | R-A-017 | Developer | 168 | 132.6 | 122.8 | -9.8 | 73.1
2027-06-01 | R-A-019 | QA Engineer | 176 | 157 | 154.4 | -2.7 | 87.7
2027-06-01 | R-A-020 | Project Manager | 176 | 143.2 | 154 | 10.8 | 87.5
2027-06-01 | R-A-023 | QA Engineer | 72 | 61.4 | 58.6 | -2.8 | 81.5
2027-07-01 | R-A-003 | Architect | 176 | 137.1 | 149.3 | 12.2 | 84.8
2027-07-01 | R-A-004 | DevOps Engineer | 176 | 160.3 | 172.1 | 11.9 | 97.8
2027-07-01 | R-A-007 | Data Engineer | 176 | 161.8 | 148 | -13.7 | 84.1
2027-07-01 | R-A-009 | DevOps Engineer | 40 | 35.5 | 36.8 | 1.3 | 91.9
2027-07-01 | R-A-010 | Project Manager | 40 | 36.5 | 39 | 2.5 | 97.6
2027-07-01 | R-A-011 | DevOps Engineer | 176 | 148.9 | 145.7 | -3.1 | 82.8
2027-07-01 | R-A-013 | Data Engineer | 176 | 149.7 | 145.8 | -3.9 | 82.8
2027-07-01 | R-A-016 | Developer | 176 | 159.8 | 156 | -3.8 | 88.6
2027-07-01 | R-A-017 | Developer | 176 | 147.7 | 152.9 | 5.2 | 86.9
2027-07-01 | R-A-019 | QA Engineer | 176 | 150.4 | 163.7 | 13.3 | 93
2027-07-01 | R-A-020 | Project Manager | 176 | 145.1 | 149.4 | 4.3 | 84.9
2027-07-01 | R-A-023 | QA Engineer | 176 | 154.3 | 160.5 | 6.2 | 91.2
2027-08-01 | R-A-003 | Architect | 176 | 144 | 130.9 | -13.1 | 74.4
2027-08-01 | R-A-004 | DevOps Engineer | 176 | 146 | 134.8 | -11.2 | 76.6
2027-08-01 | R-A-007 | Data Engineer | 152 | 132 | 129 | -2.9 | 84.9
2027-08-01 | R-A-009 | DevOps Engineer | 176 | 150.5 | 156.4 | 5.9 | 88.8
2027-08-01 | R-A-010 | Project Manager | 176 | 158.5 | 165.7 | 7.2 | 94.1
2027-08-01 | R-A-011 | DevOps Engineer | 176 | 153.7 | 164 | 10.3 | 93.2
2027-08-01 | R-A-013 | Data Engineer | 176 | 155.1 | 148.2 | -6.8 | 84.2
2027-08-01 | R-A-016 | Developer | 80 | 72.2 | 71.4 | -0.8 | 89.3
2027-08-01 | R-A-017 | Developer | 176 | 141.9 | 155.5 | 13.6 | 88.4
2027-08-01 | R-A-019 | QA Engineer | 80 | 67.7 | 69.6 | 2 | 87
2027-08-01 | R-A-020 | Project Manager | 176 | 141.2 | 154.4 | 13.2 | 87.7
2027-08-01 | R-A-023 | QA Engineer | 176 | 159.1 | 146.1 | -13 | 83
2027-09-01 | R-A-003 | Architect | 176 | 137.8 | 150.8 | 13 | 85.7
2027-09-01 | R-A-004 | DevOps Engineer | 160 | 132.9 | 145.9 | 13 | 91.2
2027-09-01 | R-A-009 | DevOps Engineer | 176 | 156.8 | 167.1 | 10.3 | 95
2027-09-01 | R-A-010 | Project Manager | 176 | 158.7 | 168.7 | 9.9 | 95.8
2027-09-01 | R-A-011 | DevOps Engineer | 176 | 144.1 | 152.4 | 8.3 | 86.6
2027-09-01 | R-A-013 | Data Engineer | 176 | 154.8 | 169.7 | 15 | 96.4
2027-09-01 | R-A-015 | QA Engineer | 48 | 42.4 | 44.9 | 2.5 | 93.6
2027-09-01 | R-A-017 | Developer | 128 | 101.8 | 94.3 | -7.5 | 73.7
2027-09-01 | R-A-020 | Project Manager | 144 | 119.1 | 121.2 | 2.1 | 84.2
2027-09-01 | R-A-023 | QA Engineer | 176 | 144.9 | 134.1 | -10.8 | 76.2
2027-10-01 | R-A-003 | Architect | 168 | 134.3 | 122.6 | -11.7 | 73
2027-10-01 | R-A-009 | DevOps Engineer | 128 | 110.3 | 112.3 | 2.1 | 87.8
2027-10-01 | R-A-010 | Project Manager | 24 | 21.4 | 21.9 | 0.5 | 91.3
2027-10-01 | R-A-011 | DevOps Engineer | 40 | 34.4 | 35.5 | 1.1 | 88.7
2027-10-01 | R-A-013 | Data Engineer | 128 | 109.3 | 99 | -10.2 | 77.4
2027-10-01 | R-A-023 | QA Engineer | 88 | 79.9 | 78.7 | -1.2 | 89.5
2027-11-01 | R-A-003 | Architect | 16 | 12.4 | 12.3 | -0.1 | 76.6

## Budget_Costs
Month | CostCategory | PlannedCost_USD | ActualCost_USD | ForecastCost_USD | CumPlanned_USD | CumActual_USD | CumForecast_USD | EV | PV | AC | CPI | SPI
2027-01-01 | Labor | 6244.11 | 5748.4 | 5717.39 | 8182.83 | 7715.16 | 7979.19 | 10319.3 | 8182.83 | 7715.16 | 1.338 | 1.261
2027-01-01 | Software | 873.72 | 837.88 | 865.4 | 8182.83 | 7715.16 | 7979.19 | 10319.3 | 8182.83 | 7715.16 | 1.338 | 1.261
2027-01-01 | Infra | 613.9 | 614.58 | 637.51 | 8182.83 | 7715.16 | 7979.19 | 10319.3 | 8182.83 | 7715.16 | 1.338 | 1.261
2027-01-01 | Travel | 99.49 | 98.1 | 99.16 | 8182.83 | 7715.16 | 7979.19 | 10319.3 | 8182.83 | 7715.16 | 1.338 | 1.261
2027-01-01 | Contingency | 351.6 | 372.21 | 377.27 | 8182.83 | 7715.16 | 7979.19 | 10319.3 | 8182.83 | 7715.16 | 1.338 | 1.261
2027-02-01 | Labor | 9809.46 | 8884.76 | 8870.91 | 21858.62 | 20486.94 | 20790.66 | 28813.15 | 21858.62 | 20486.94 | 1.406 | 1.318
2027-02-01 | Software | 912.35 | 995.11 | 955.45 | 21858.62 | 20486.94 | 20790.66 | 28813.15 | 21858.62 | 20486.94 | 1.406 | 1.318
2027-02-01 | Infra | 1797.23 | 1864.38 | 1882.46 | 21858.62 | 20486.94 | 20790.66 | 28813.15 | 21858.62 | 20486.94 | 1.406 | 1.318
2027-02-01 | Travel | 260.47 | 259.13 | 256.35 | 21858.62 | 20486.94 | 20790.66 | 28813.15 | 21858.62 | 20486.94 | 1.406 | 1.318
2027-02-01 | Contingency | 896.3 | 823.02 | 820.81 | 21858.62 | 20486.94 | 20790.66 | 28813.15 | 21858.62 | 20486.94 | 1.406 | 1.318
2027-03-01 | Labor | 26892.22 | 26210.26 | 26502.68 | 58578.88 | 56929.6 | 58864.42 | 85260.06 | 58578.88 | 56929.6 | 1.498 | 1.455
2027-03-01 | Software | 1505.91 | 1370.82 | 1375.66 | 58578.88 | 56929.6 | 58864.42 | 85260.06 | 58578.88 | 56929.6 | 1.498 | 1.455
2027-03-01 | Infra | 5203.48 | 4982.46 | 5061.84 | 58578.88 | 56929.6 | 58864.42 | 85260.06 | 58578.88 | 56929.6 | 1.498 | 1.455
2027-03-01 | Travel | 873.12 | 840.37 | 883.11 | 58578.88 | 56929.6 | 58864.42 | 85260.06 | 58578.88 | 56929.6 | 1.498 | 1.455
2027-03-01 | Contingency | 2245.52 | 2067.49 | 2106.65 | 58578.88 | 56929.6 | 58864.42 | 85260.06 | 58578.88 | 56929.6 | 1.498 | 1.455
2027-04-01 | Labor | 52642.03 | 54490.45 | 51219.15 | 124660.94 | 124962.51 | 127293.75 | 226929 | 124660.94 | 124962.51 | 1.816 | 1.82
2027-04-01 | Software | 5560.4 | 5623.49 | 5471.33 | 124660.94 | 124962.51 | 127293.75 | 226929 | 124660.94 | 124962.51 | 1.816 | 1.82
2027-04-01 | Infra | 3539.27 | 3616.42 | 3679.65 | 124660.94 | 124962.51 | 127293.75 | 226929 | 124660.94 | 124962.51 | 1.816 | 1.82
2027-04-01 | Travel | 1113 | 1148.13 | 1181.88 | 124660.94 | 124962.51 | 127293.75 | 226929 | 124660.94 | 124962.51 | 1.816 | 1.82
2027-04-01 | Contingency | 3227.38 | 3352.26 | 3253.11 | 124660.94 | 124962.51 | 127293.75 | 226929 | 124660.94 | 124962.51 | 1.816 | 1.82
2027-05-01 | Labor | 88419.6 | 88883.15 | 89551.21 | 240734.53 | 240779.85 | 242676.26 | 518117.72 | 240734.53 | 240779.85 | 2.152 | 2.152
2027-05-01 | Software | 5687.6 | 5297.9 | 5662.85 | 240734.53 | 240779.85 | 242676.26 | 518117.72 | 240734.53 | 240779.85 | 2.152 | 2.152
2027-05-01 | Infra | 13139.3 | 12644.31 | 12399.99 | 240734.53 | 240779.85 | 242676.26 | 518117.72 | 240734.53 | 240779.85 | 2.152 | 2.152
2027-05-01 | Travel | 1130.3 | 1090.6 | 1134.64 | 240734.53 | 240779.85 | 242676.26 | 518117.72 | 240734.53 | 240779.85 | 2.152 | 2.152
2027-05-01 | Contingency | 7696.79 | 8376.27 | 7739.59 | 240734.53 | 240779.85 | 242676.26 | 518117.72 | 240734.53 | 240779.85 | 2.152 | 2.152
2027-06-01 | Labor | 171978.45 | 171622.79 | 166964.54 | 461200.51 | 459162.6 | 453362.38 | 817368.57 | 461200.51 | 459162.6 | 1.78 | 1.772
2027-06-01 | Software | 10001.95 | 10358.45 | 10710.75 | 461200.51 | 459162.6 | 453362.38 | 817368.57 | 461200.51 | 459162.6 | 1.78 | 1.772
2027-06-01 | Infra | 20029.81 | 20402.9 | 19351.93 | 461200.51 | 459162.6 | 453362.38 | 817368.57 | 461200.51 | 459162.6 | 1.78 | 1.772
2027-06-01 | Travel | 4636.64 | 4661.62 | 4514.14 | 461200.51 | 459162.6 | 453362.38 | 817368.57 | 461200.51 | 459162.6 | 1.78 | 1.772
2027-06-01 | Contingency | 13819.12 | 13289.63 | 14102.68 | 461200.51 | 459162.6 | 453362.38 | 817368.57 | 461200.51 | 459162.6 | 1.78 | 1.772
2027-07-01 | Labor | 202587.32 | 207354.27 | 210420.17 | 738529.62 | 740532.43 | 725565.67 | 1144046.39 | 738529.62 | 740532.43 | 1.545 | 1.549
2027-07-01 | Software | 25674.89 | 25976.44 | 25690.91 | 738529.62 | 740532.43 | 725565.67 | 1144046.39 | 738529.62 | 740532.43 | 1.545 | 1.549
2027-07-01 | Infra | 33350.76 | 34471.67 | 33886.38 | 738529.62 | 740532.43 | 725565.67 | 1144046.39 | 738529.62 | 740532.43 | 1.545 | 1.549
2027-07-01 | Travel | 4371.41 | 4243.91 | 4113.6 | 738529.62 | 740532.43 | 725565.67 | 1144046.39 | 738529.62 | 740532.43 | 1.545 | 1.549
2027-07-01 | Contingency | 11344.73 | 11111.19 | 10995.15 | 738529.62 | 740532.43 | 725565.67 | 1144046.39 | 738529.62 | 740532.43 | 1.545 | 1.549
2027-08-01 | Labor | 209794.64 | 208949.62 | 207941.41 | 1012033.28 | 1015706.22 | 998976.05 | 1206132.6 | 1012033.28 | 1015706.22 | 1.187 | 1.192
2027-08-01 | Software | 19495.89 | 20235.21 | 19740.98 | 1012033.28 | 1015706.22 | 998976.05 | 1206132.6 | 1012033.28 | 1015706.22 | 1.187 | 1.192
2027-08-01 | Infra | 23216.59 | 22575.13 | 21869.7 | 1012033.28 | 1015706.22 | 998976.05 | 1206132.6 | 1012033.28 | 1015706.22 | 1.187 | 1.192
2027-08-01 | Travel | 7469.88 | 7375.33 | 7687.82 | 1012033.28 | 1015706.22 | 998976.05 | 1206132.6 | 1012033.28 | 1015706.22 | 1.187 | 1.192
2027-08-01 | Contingency | 13526.67 | 12460.4 | 13203.67 | 1012033.28 | 1015706.22 | 998976.05 | 1206132.6 | 1012033.28 | 1015706.22 | 1.187 | 1.192
2027-09-01 | Labor | 172292.43 | 180402.19 | 171374.05 | 1241826.81 | 1251630.83 | 1243146.47 | 1343761.5 | 1241826.81 | 1251630.83 | 1.074 | 1.082
2027-09-01 | Software | 12432.14 | 12793.77 | 12210.03 | 1241826.81 | 1251630.83 | 1243146.47 | 1343761.5 | 1241826.81 | 1251630.83 | 1.074 | 1.082
2027-09-01 | Infra | 28750.04 | 26724.25 | 28248.13 | 1241826.81 | 1251630.83 | 1243146.47 | 1343761.5 | 1241826.81 | 1251630.83 | 1.074 | 1.082
2027-09-01 | Travel | 2249.31 | 2070.62 | 2051.13 | 1241826.81 | 1251630.83 | 1243146.47 | 1343761.5 | 1241826.81 | 1251630.83 | 1.074 | 1.082
2027-09-01 | Contingency | 14069.61 | 13382.93 | 14273.96 | 1241826.81 | 1251630.83 | 1243146.47 | 1343761.5 | 1241826.81 | 1251630.83 | 1.074 | 1.082
2027-10-01 | Labor | 73424.71 | 69680.78 | 72113.53 | 1340503.06 | 1348166.72 | 1338816.69 | 1343761.5 | 1340503.06 | 1348166.72 | 0.997 | 1.002
2027-10-01 | Software | 8281.93 | 9062.04 | 9009.29 | 1340503.06 | 1348166.72 | 1338816.69 | 1343761.5 | 1340503.06 | 1348166.72 | 0.997 | 1.002
2027-10-01 | Infra | 8781.08 | 8458.18 | 8665.84 | 1340503.06 | 1348166.72 | 1338816.69 | 1343761.5 | 1340503.06 | 1348166.72 | 0.997 | 1.002
2027-10-01 | Travel | 2389.93 | 2361.14 | 2337.53 | 1340503.06 | 1348166.72 | 1338816.69 | 1343761.5 | 1340503.06 | 1348166.72 | 0.997 | 1.002
2027-10-01 | Contingency | 5798.6 | 5762.56 | 5530.98 | 1340503.06 | 1348166.72 | 1338816.69 | 1343761.5 | 1340503.06 | 1348166.72 | 0.997 | 1.002
2027-11-01 | Labor | 2625.82 | 2604.65 | 2720.01 | 1343761.5 | 1351423.09 | 1342036.26 | 1343761.5 | 1343761.5 | 1351423.09 | 0.994 | 1
2027-11-01 | Software | 252.54 | 256.59 | 256.8 | 1343761.5 | 1351423.09 | 1342036.26 | 1343761.5 | 1343761.5 | 1351423.09 | 0.994 | 1
2027-11-01 | Infra | 146.1 | 159.38 | 149.26 | 1343761.5 | 1351423.09 | 1342036.26 | 1343761.5 | 1343761.5 | 1351423.09 | 0.994 | 1
2027-11-01 | Travel | 64.99 | 68.09 | 67.55 | 1343761.5 | 1351423.09 | 1342036.26 | 1343761.5 | 1343761.5 | 1351423.09 | 0.994 | 1
2027-11-01 | Contingency | 168.98 | 153.47 | 159.7 | 1343761.5 | 1351423.09 | 1342036.26 | 1343761.5 | 1343761.5 | 1351423.09 | 0.994 | 1

## Milestones
MilestoneID | MilestoneName | PlannedDate | ActualDate | Status | SlippageDays | Owner | Critical
MS-001 | Hypercare Complete | 2027-01-20 | 2027-01-20 | Not Started | 0 | River Tribe Elder | TRUE
MS-002 | Training Complete | 2027-02-08 | 2027-02-12 | Not Started | 4 | W'Kabi | FALSE
MS-003 | UAT Start | 2027-02-27 | 2027-02-27 | Not Started | 0 | Jabari Elder (3) | FALSE
MS-004 | Performance Test | 2027-03-19 | 2027-03-25 | Not Started | 6 | W'Kabi (21) | FALSE
MS-005 | Architecture Review | 2027-04-07 | 2027-04-07 | Not Started | 0 | M'Baku | FALSE
MS-006 | UAT Start | 2027-04-26 | 2027-04-25 | Not Started | -1 | T'Challa (20) | FALSE
MS-007 | UAT Start | 2027-05-15 | 2027-05-21 | Not Started | 6 | M'Baku | FALSE
MS-008 | Go-Live | 2027-06-04 | 2027-06-04 | Not Started | 0 | Jabari Elder (4) | FALSE
MS-009 | UAT Start | 2027-06-23 | 2027-06-26 | Not Started | 3 | M'Baku | FALSE
MS-010 | Design Complete | 2027-07-12 | 2027-07-07 | Not Started | -5 | M'Baku (11) | FALSE
MS-011 | Architecture Review | 2027-07-31 | 2027-08-07 | Not Started | 7 | Nakia (15) | TRUE
MS-012 | Security Assessment | 2027-08-20 | 2027-08-19 | Not Started | -1 | Jabari Elder (3) | FALSE
MS-013 | Hypercare Complete | 2027-09-08 | 2027-09-11 | Not Started | 3 | W'Kabi | FALSE
MS-014 | Architecture Review | 2027-09-27 | 2027-10-01 | Not Started | 4 | River Tribe Elder (12) | TRUE
MS-015 | Architecture Review | 2027-10-16 | 2027-10-23 | Not Started | 7 | Okoye (19) | FALSE

## Risks_Issues_Dependencies
RID_ID | Type | Title | Description | Owner | ImpactArea | Probability_pct | Impact | Severity | ExposureScore | Status | TargetDate | Linkage
RID-001 | Risk | Risk #1 | Synthetic risk description for test purposes. | M'Baku (11) | Cost | 61 | Medium |  | 122 | Closed | 2027-06-02 | External-API
RID-002 | Issue | Issue #2 | Synthetic issue description for test purposes. | River Tribe Elder | Quality |  | High | Medium |  | Open | 2027-04-17 | Data-Center
RID-003 | Risk | Risk #3 | Synthetic risk description for test purposes. | River Tribe Elder | Cost | 58 | Medium |  | 116 | Closed | 2027-03-31 | Data-Center
RID-004 | Dependency | Dependency #4 | Synthetic dependency description for test purposes. | W'Kabi | Scope |  | Medium |  |  | Transferred | 2027-10-18 | Data-Center
RID-005 | Risk | Risk #5 | Synthetic risk description for test purposes. | Zuri (24) | Cost | 70 | Low |  | 70 | Closed | 2027-03-24 | MS-001
RID-006 | Issue | Issue #6 | Synthetic issue description for test purposes. | M'Baku (11) | Quality |  | High | Medium |  | Mitigated | 2027-07-29 | MS-005
RID-007 | Dependency | Dependency #7 | Synthetic dependency description for test purposes. | M'Baku (11) | Cost |  | Low |  |  | Closed | 2027-02-27 | Vendor-Contract
RID-008 | Risk | Risk #8 | Synthetic risk description for test purposes. | River Tribe Elder | Scope | 22 | High |  | 66 | Mitigated | 2027-09-05 | MS-001
RID-009 | Risk | Risk #9 | Synthetic risk description for test purposes. | Jabari Elder (6) | Cost | 72 | High |  | 216 | Open | 2027-08-12 | Vendor-Contract
RID-010 | Risk | Risk #10 | Synthetic risk description for test purposes. | W'Kabi | People | 63 | Low |  | 63 | Open | 2027-02-09 | External-API
RID-011 | Issue | Issue #11 | Synthetic issue description for test purposes. | T'Challa (20) | People |  | Medium | Low |  | Open | 2027-03-22 | MS-001
RID-012 | Risk | Risk #12 | Synthetic risk description for test purposes. | Shuri (18) | People | 15 | Medium |  | 30 | Accepted | 2027-10-03 | MS-001
RID-013 | Issue | Issue #13 | Synthetic issue description for test purposes. | Okoye (16) | Schedule |  | Medium | Low |  | Open | 2027-09-05 | External-API
RID-014 | Risk | Risk #14 | Synthetic risk description for test purposes. | Jabari Elder | Cost | 35 | Low |  | 35 | Closed | 2027-03-02 | Vendor-Contract
RID-015 | Risk | Risk #15 | Synthetic risk description for test purposes. | Ayo | Scope | 64 | Low |  | 64 | Mitigated | 2027-09-10 | MS-005
RID-016 | Issue | Issue #16 | Synthetic issue description for test purposes. | Okoye | Schedule |  | Low | Low |  | Transferred | 2027-04-20 | Vendor-Contract
RID-017 | Issue | Issue #17 | Synthetic issue description for test purposes. | Ayo | Security |  | Medium | Low |  | Open | 2027-04-15 | MS-001

## Operational_KPIs
WeekStart | KPI | PlannedValue | ActualValue | Unit | Notes
2026-12-28 | Build Velocity | 33.28 | 30.78 | points
2026-12-28 | Defect Leakage | 5.68 | 6.88 | defects
2026-12-28 | Cycle Time | 6.72 | 7.71 | days
2026-12-28 | MTTR | 7.09 | 9.09 | hours
2027-01-04 | Build Velocity | 39.85 | 39.83 | points
2027-01-04 | Defect Leakage | 11.24 | 10.29 | defects
2027-01-04 | Cycle Time | 7.01 | 7.45 | days
2027-01-04 | MTTR | 4.63 | 4.73 | hours
2027-01-11 | Build Velocity | 52.89 | 53.37 | points
2027-01-11 | Defect Leakage | 5.21 | 2.94 | defects
2027-01-11 | Cycle Time | 6.3 | 5.38 | days
2027-01-11 | MTTR | 8.82 | 7.92 | hours
2027-01-18 | Build Velocity | 47.59 | 46.18 | points
2027-01-18 | Defect Leakage | 2.42 | 2.9 | defects
2027-01-18 | Cycle Time | 4.76 | 5.71 | days
2027-01-18 | MTTR | 6.2 | 7.97 | hours
2027-01-25 | Build Velocity | 57.92 | 52.99 | points
2027-01-25 | Defect Leakage | 8.38 | 6.62 | defects
2027-01-25 | Cycle Time | 7.01 | 7.28 | days
2027-01-25 | MTTR | 11.62 | 8.13 | hours
2027-02-01 | Build Velocity | 44.3 | 46.8 | points
2027-02-01 | Defect Leakage | 2.35 | 1.3 | defects
2027-02-01 | Cycle Time | 6.89 | 6.09 | days
2027-02-01 | MTTR | 7.06 | 7.04 | hours
2027-02-08 | Build Velocity | 44.2 | 45.79 | points
2027-02-08 | Defect Leakage | 11.49 | 9.16 | defects
2027-02-08 | Cycle Time | 6.82 | 6.73 | days
2027-02-08 | MTTR | 8.24 | 7.24 | hours
2027-02-15 | Build Velocity | 45.98 | 43.68 | points
2027-02-15 | Defect Leakage | 3.13 | 3.41 | defects
2027-02-15 | Cycle Time | 5.5 | 4.91 | days
2027-02-15 | MTTR | 8.49 | 6.65 | hours
2027-02-22 | Build Velocity | 30.41 | 30.08 | points
2027-02-22 | Defect Leakage | 11.96 | 8.72 | defects
2027-02-22 | Cycle Time | 7.58 | 7.17 | days
2027-02-22 | MTTR | 4.98 | 5.96 | hours
2027-03-01 | Build Velocity | 38.08 | 41.12 | points
2027-03-01 | Defect Leakage | 6.45 | 3.68 | defects
2027-03-01 | Cycle Time | 6.41 | 7.2 | days
2027-03-01 | MTTR | 6.56 | 5.53 | hours
2027-03-08 | Build Velocity | 22.6 | 22.79 | points
2027-03-08 | Defect Leakage | 10.91 | 12.89 | defects
2027-03-08 | Cycle Time | 6.56 | 7.63 | days
2027-03-08 | MTTR | 9.1 | 10.52 | hours
2027-03-15 | Build Velocity | 40.35 | 37.29 | points
2027-03-15 | Defect Leakage | 4.01 | 2.45 | defects
2027-03-15 | Cycle Time | 6.95 | 4.96 | days
2027-03-15 | MTTR | 8.43 | 7.24 | hours
2027-03-22 | Build Velocity | 52.15 | 52.69 | points
2027-03-22 | Defect Leakage | 8.12 | 4.62 | defects
2027-03-22 | Cycle Time | 4.55 | 5.45 | days
2027-03-22 | MTTR | 9.75 | 9.44 | hours
2027-03-29 | Build Velocity | 50.77 | 54.05 | points
2027-03-29 | Defect Leakage | 2.74 | 3.5 | defects
2027-03-29 | Cycle Time | 6.21 | 5.75 | days
2027-03-29 | MTTR | 9.44 | 7.94 | hours
2027-04-05 | Build Velocity | 55.12 | 58.21 | points
2027-04-05 | Defect Leakage | 8.4 | 5.42 | defects
2027-04-05 | Cycle Time | 7.83 | 7.18 | days
2027-04-05 | MTTR | 11.29 | 7.21 | hours
2027-04-12 | Build Velocity | 24.97 | 23.23 | points
2027-04-12 | Defect Leakage | 3.65 | 2.76 | defects
2027-04-12 | Cycle Time | 6.55 | 5.72 | days
2027-04-12 | MTTR | 11.53 | 14.14 | hours
2027-04-19 | Build Velocity | 53.84 | 51.15 | points
2027-04-19 | Defect Leakage | 8.35 | 7.86 | defects
2027-04-19 | Cycle Time | 3.63 | 3.09 | days
2027-04-19 | MTTR | 8.27 | 7.87 | hours
2027-04-26 | Build Velocity | 26.75 | 29.11 | points
2027-04-26 | Defect Leakage | 3.54 | 3.64 | defects
2027-04-26 | Cycle Time | 6.6 | 6.62 | days
2027-04-26 | MTTR | 10.74 | 10.68 | hours
2027-05-03 | Build Velocity | 53.01 | 48.01 | points
2027-05-03 | Defect Leakage | 2.45 | 2.49 | defects
2027-05-03 | Cycle Time | 5.88 | 6.03 | days
2027-05-03 | MTTR | 10.14 | 9.04 | hours
2027-05-10 | Build Velocity | 45.56 | 45.54 | points
2027-05-10 | Defect Leakage | 8.27 | 6.05 | defects
2027-05-10 | Cycle Time | 7.78 | 7.33 | days
2027-05-10 | MTTR | 10.44 | 11.27 | hours
2027-05-17 | Build Velocity | 31.9 | 29.17 | points
2027-05-17 | Defect Leakage | 2.6 | 2.21 | defects
2027-05-17 | Cycle Time | 5.42 | 4.35 | days
2027-05-17 | MTTR | 8.85 | 7.25 | hours
2027-05-24 | Build Velocity | 48.73 | 51.02 | points
2027-05-24 | Defect Leakage | 10.61 | 13.58 | defects
2027-05-24 | Cycle Time | 3.65 | 3.23 | days
2027-05-24 | MTTR | 8.49 | 6.99 | hours
2027-05-31 | Build Velocity | 38.66 | 36.86 | points
2027-05-31 | Defect Leakage | 4.48 | 2.59 | defects
2027-05-31 | Cycle Time | 4.45 | 3.97 | days
2027-05-31 | MTTR | 8.92 | 6.9 | hours
2027-06-07 | Build Velocity | 54.61 | 50.9 | points
2027-06-07 | Defect Leakage | 5.27 | 5.07 | defects
2027-06-07 | Cycle Time | 4.56 | 4.94 | days
2027-06-07 | MTTR | 7.99 | 7.67 | hours
2027-06-14 | Build Velocity | 39.95 | 38.42 | points
2027-06-14 | Defect Leakage | 2.23 | 2.8 | defects
2027-06-14 | Cycle Time | 5.53 | 6.54 | days
2027-06-14 | MTTR | 5.72 | 4.85 | hours
2027-06-21 | Build Velocity | 22.02 | 22 | points
2027-06-21 | Defect Leakage | 10.82 | 11.08 | defects
2027-06-21 | Cycle Time | 5.35 | 5.18 | days
2027-06-21 | MTTR | 10.78 | 9.72 | hours
2027-06-28 | Build Velocity | 55.3 | 57.81 | points
2027-06-28 | Defect Leakage | 9.64 | 7.64 | defects
2027-06-28 | Cycle Time | 5 | 4.93 | days
2027-06-28 | MTTR | 5.56 | 5.49 | hours
2027-07-05 | Build Velocity | 22.94 | 22.96 | points
2027-07-05 | Defect Leakage | 9.64 | 6.98 | defects
2027-07-05 | Cycle Time | 7.95 | 8.26 | days
2027-07-05 | MTTR | 4.95 | 6.35 | hours
2027-07-12 | Build Velocity | 35.76 | 37.87 | points
2027-07-12 | Defect Leakage | 5.39 | 6.74 | defects
2027-07-12 | Cycle Time | 6.77 | 5.42 | days
2027-07-12 | MTTR | 8.07 | 7.67 | hours
2027-07-19 | Build Velocity | 21.81 | 20.23 | points
2027-07-19 | Defect Leakage | 5.33 | 4.69 | defects
2027-07-19 | Cycle Time | 5.28 | 5.3 | days
2027-07-19 | MTTR | 8.12 | 6.74 | hours
2027-07-26 | Build Velocity | 44.52 | 41.52 | points
2027-07-26 | Defect Leakage | 11.91 | 13 | defects
2027-07-26 | Cycle Time | 4.5 | 3.9 | days
2027-07-26 | MTTR | 10.63 | 10.34 | hours
2027-08-02 | Build Velocity | 48.35 | 46.41 | points
2027-08-02 | Defect Leakage | 10.16 | 8.07 | defects
2027-08-02 | Cycle Time | 6.37 | 7.58 | days
2027-08-02 | MTTR | 8.67 | 10.04 | hours
2027-08-09 | Build Velocity | 49.01 | 50.86 | points
2027-08-09 | Defect Leakage | 2.27 | 1.99 | defects
2027-08-09 | Cycle Time | 7.84 | 8.55 | days
2027-08-09 | MTTR | 10.21 | 10.25 | hours
2027-08-16 | Build Velocity | 48.86 | 49.67 | points
2027-08-16 | Defect Leakage | 3.71 | 3.72 | defects
2027-08-16 | Cycle Time | 6.1 | 6.83 | days
2027-08-16 | MTTR | 5.18 | 5.58 | hours
2027-08-23 | Build Velocity | 21.26 | 23.17 | points
2027-08-23 | Defect Leakage | 3.1 | 1.6 | defects
2027-08-23 | Cycle Time | 4.57 | 3.54 | days
2027-08-23 | MTTR | 9.52 | 8.45 | hours
2027-08-30 | Build Velocity | 51 | 55.29 | points
2027-08-30 | Defect Leakage | 10.73 | 11.68 | defects
2027-08-30 | Cycle Time | 3.31 | 2.55 | days
2027-08-30 | MTTR | 5.66 | 4.68 | hours
2027-09-06 | Build Velocity | 46.49 | 46.73 | points
2027-09-06 | Defect Leakage | 5.14 | 3.28 | defects
2027-09-06 | Cycle Time | 7.56 | 6.59 | days
2027-09-06 | MTTR | 6.83 | 7.79 | hours
2027-09-13 | Build Velocity | 48.84 | 50.24 | points
2027-09-13 | Defect Leakage | 8.93 | 8.83 | defects
2027-09-13 | Cycle Time | 3.96 | 3.26 | days
2027-09-13 | MTTR | 8.46 | 6.41 | hours
2027-09-20 | Build Velocity | 58.92 | 56.53 | points
2027-09-20 | Defect Leakage | 4.89 | 3.26 | defects
2027-09-20 | Cycle Time | 6.52 | 5.6 | days
2027-09-20 | MTTR | 6.79 | 8.51 | hours
2027-09-27 | Build Velocity | 51.82 | 49.47 | points
2027-09-27 | Defect Leakage | 3.22 | 3.35 | defects
2027-09-27 | Cycle Time | 4.9 | 5.83 | days
2027-09-27 | MTTR | 10.55 | 13.38 | hours
2027-10-04 | Build Velocity | 52.18 | 50 | points
2027-10-04 | Defect Leakage | 4.88 | 5.22 | defects
2027-10-04 | Cycle Time | 4.73 | 4.36 | days
2027-10-04 | MTTR | 6.05 | 5.66 | hours
2027-10-11 | Build Velocity | 28.08 | 28.3 | points
2027-10-11 | Defect Leakage | 11.33 | 11.98 | defects
2027-10-11 | Cycle Time | 3.69 | 3.72 | days
2027-10-11 | MTTR | 8.69 | 6.69 | hours
2027-10-18 | Build Velocity | 46.79 | 47.08 | points
2027-10-18 | Defect Leakage | 8.38 | 4.54 | defects
2027-10-18 | Cycle Time | 5.07 | 5.36 | days
2027-10-18 | MTTR | 4.8 | 5.47 | hours
2027-10-25 | Build Velocity | 20.21 | 20.41 | points
2027-10-25 | Defect Leakage | 11.29 | 9.32 | defects
2027-10-25 | Cycle Time | 7.68 | 8.74 | days
2027-10-25 | MTTR | 7.82 | 5.78 | hours
2027-11-01 | Build Velocity | 58.56 | 56.46 | points
2027-11-01 | Defect Leakage | 8.46 | 10.37 | defects
2027-11-01 | Cycle Time | 3.45 | 3.4 | days
2027-11-01 | MTTR | 8.28 | 9.16 | hours

## Data_Dictionary
Sheet | Column | Description
Project_Overview | ProjectID | Global unique project ID
Project_Overview | ProjectName | Fictional project name
Project_Overview | DatasetSet | SetA/SetB/SetC
Project_Overview | ProjectTheme | Fictional universe label
Project_Overview | Sponsor | Fictional sponsor
Project_Overview | ProjectManager | Fictional PM
Project_Overview | Portfolio | Portfolio grouping
Project_Overview | Domain | Solution domain
Project_Overview | DeliveryMethod | Agile/Hybrid/Waterfall
Project_Overview | StartDate | Planned start date
Project_Overview | EndDate | Planned end date
Project_Overview | CurrentPhase | Current phase at time of generation
Project_Overview | HealthRAG | Red/Amber/Green overall health
Project_Overview | Complexity | Low/Medium/High
Project_Overview | RiskProfile | Low/Medium/High
Project_Overview | Maturity | Emerging/Defined/Optimized
Project_Overview | Description | Short description
Resources | ResourceID | Unique resource key
Resources | ResourceName | Fictional name
Resources | Role | Role on project
Resources | SkillTier | Junior/Mid/Senior/Principal
Resources | Location | Fictional/Generic location
Resources | CostRate_USD_per_hour | Internal cost rate ($/hr)
Resources | BillRate_USD_per_hour | External bill rate ($/hr)
Resources | UtilizationTarget_pct | Target utilization %
Resources | AllocationStart | Allocation start date
Resources | AllocationEnd | Allocation end date
Capacity_Effort | Month | First day of month
Capacity_Effort | ResourceID | FK to Resources
Capacity_Effort | Role | Role on project
Capacity_Effort | CapacityHours | Capacity hours in month
Capacity_Effort | PlannedHours | Planned hours
Capacity_Effort | ActualHours | Actual hours
Capacity_Effort | VarianceHours | Actual - Planned
Capacity_Effort | Utilization_pct | Actual/Capacity*100
Budget_Costs | Month | First day of month
Budget_Costs | CostCategory | Labor/Software/Infra/Travel/Contingency
Budget_Costs | PlannedCost_USD | Planned monthly cost
Budget_Costs | ActualCost_USD | Actual monthly cost
Budget_Costs | ForecastCost_USD | Forecast monthly cost
Budget_Costs | CumPlanned_USD | Cumulative planned cost
Budget_Costs | CumActual_USD | Cumulative actual cost
Budget_Costs | CumForecast_USD | Cumulative forecast cost
Budget_Costs | EV | Earned Value (cumulative)
Budget_Costs | PV | Planned Value (cumulative)
Budget_Costs | AC | Actual Cost (cumulative)
Budget_Costs | CPI | EV/AC
Budget_Costs | SPI | EV/PV
Milestones | MilestoneID | Unique milestone ID
Milestones | MilestoneName | Milestone title
Milestones | PlannedDate | Planned completion date
Milestones | ActualDate | Actual completion date (optional)
Milestones | Status | Status string
Milestones | SlippageDays | Actual - Planned (days)
Milestones | Owner | Responsible resource
Milestones | Critical | Critical path flag
Risks_Issues_Dependencies | RID_ID | Unique RID ID
Risks_Issues_Dependencies | Type | Risk/Issue/Dependency
Risks_Issues_Dependencies | Title | Short title
Risks_Issues_Dependencies | Description | Narrative description
Risks_Issues_Dependencies | Owner | Responsible resource
Risks_Issues_Dependencies | ImpactArea | Scope/Cost/Schedule/Quality/People/Security
Risks_Issues_Dependencies | Probability_pct | Probability for Risks (0-100%)
Risks_Issues_Dependencies | Impact | Impact level (Low/Medium/High)
Risks_Issues_Dependencies | Severity | Issue severity (Low/Medium/High)
Risks_Issues_Dependencies | ExposureScore | Risk exposure (prob*impact weight)
Risks_Issues_Dependencies | Status | Open/Mitigated/Closed/Transferred/Accepted
Risks_Issues_Dependencies | TargetDate | Target resolve date
Risks_Issues_Dependencies | Linkage | Related milestone/dependency
Operational_KPIs | WeekStart | Week start date (Monday)
Operational_KPIs | KPI | KPI name
Operational_KPIs | PlannedValue | Planned value
Operational_KPIs | ActualValue | Actual value
Operational_KPIs | Unit | Unit of measure
Operational_KPIs | Notes | Notes