## Project_Overview
ProjectID | ProjectName | DatasetSet | ProjectTheme | Sponsor | ProjectManager | Portfolio | Domain | DeliveryMethod | StartDate | EndDate | CurrentPhase | HealthRAG | Complexity | RiskProfile | Maturity | Description
PRJ-A-003 | Hyrule Forms Modernization | SetA | The Legend of Zelda | Tingle | Impa | Digital Delivery | IDP | Agile | 2025-03-14 | 2025-07-11 | Deploy | Amber | Low | Low | Optimized | Hyrule Forms Modernization delivering IDP capabilities using Agile methods within the The Legend of Zelda universe.

## Resources
ResourceID | ResourceName | Role | SkillTier | Location | CostRate_USD_per_hour | BillRate_USD_per_hour | UtilizationTarget_pct | AllocationStart | AllocationEnd
R-A-001 | Link | QA Engineer | Principal | The Legend of Zelda – Remote | 113.36 | 148.55 | 82.7 | 2025-06-25 | 2025-04-11
R-A-002 | Link (1) | Developer | Mid | The Legend of Zelda – Remote | 128.49 | 198.1 | 80.1 | 2025-04-26 | 2025-07-07
R-A-003 | Mipha | Developer | Principal | The Legend of Zelda – Remote | 123.95 | 165.71 | 88.3 | 2025-05-18 | 2025-05-08
R-A-004 | Sidon | Business Analyst | Mid | The Legend of Zelda – Remote | 113.46 | 151.26 | 84.8 | 2025-04-14 | 2025-03-28
R-A-005 | Sidon (4) | Developer | Senior | The Legend of Zelda – Remote | 88.84 | 141.18 | 83 | 2025-06-14 | 2025-06-09
R-A-006 | Zelda | Project Manager | Junior | The Legend of Zelda – Remote | 139.22 | 217.43 | 86.7 | 2025-05-12 | 2025-05-06
R-A-007 | Revali | Developer | Senior | The Legend of Zelda – Remote | 124.89 | 207.99 | 86.9 | 2025-06-03 | 2025-05-04
R-A-008 | Mipha (7) | Developer | Principal | The Legend of Zelda – Remote | 87.67 | 147.36 | 81.5 | 2025-06-17 | 2025-06-13
R-A-009 | Tingle | Developer | Mid | The Legend of Zelda – Remote | 126.16 | 209.52 | 87.6 | 2025-06-09 | 2025-07-02
R-A-010 | Rauru | UX Designer | Senior | The Legend of Zelda – Remote | 127.24 | 189.14 | 80.8 | 2025-05-25 | 2025-04-11

## Capacity_Effort
Month | ResourceID | Role | CapacityHours | PlannedHours | ActualHours | VarianceHours | Utilization_pct
2025-04-01 | R-A-002 | Developer | 24 | 18.4 | 18.4 | 0 | 76.7
2025-05-01 | R-A-002 | Developer | 176 | 142 | 137.1 | -4.9 | 77.9
2025-06-01 | R-A-002 | Developer | 168 | 134.8 | 126.9 | -7.9 | 75.5
2025-06-01 | R-A-009 | Developer | 128 | 113.1 | 113.3 | 0.2 | 88.5
2025-07-01 | R-A-002 | Developer | 40 | 33 | 33.1 | 0.1 | 82.8
2025-07-01 | R-A-009 | Developer | 16 | 14 | 13.9 | -0.1 | 86.6

## Budget_Costs
Month | CostCategory | PlannedCost_USD | ActualCost_USD | ForecastCost_USD | CumPlanned_USD | CumActual_USD | CumForecast_USD | EV | PV | AC | CPI | SPI
2025-03-01 | Labor | 0 | 0 | 0 | 0 | 0 | 0 | 1950.63 | 0 | 0
2025-03-01 | Software | 0 | 0 | 0 | 0 | 0 | 0 | 1950.63 | 0 | 0
2025-03-01 | Infra | 0 | 0 | 0 | 0 | 0 | 0 | 1950.63 | 0 | 0
2025-03-01 | Travel | 0 | 0 | 0 | 0 | 0 | 0 | 1950.63 | 0 | 0
2025-03-01 | Contingency | 0 | 0 | 0 | 0 | 0 | 0 | 1950.63 | 0 | 0
2025-04-01 | Labor | 2364.22 | 2364.22 | 2371.03 | 3332.94 | 3348.28 | 3355.28 | 17376.23 | 3332.94 | 3348.28 | 5.19 | 5.213
2025-04-01 | Software | 217.59 | 224.28 | 226.65 | 3332.94 | 3348.28 | 3355.28 | 17376.23 | 3332.94 | 3348.28 | 5.19 | 5.213
2025-04-01 | Infra | 470.31 | 455.99 | 448.91 | 3332.94 | 3348.28 | 3355.28 | 17376.23 | 3332.94 | 3348.28 | 5.19 | 5.213
2025-04-01 | Travel | 59.81 | 55.97 | 54.65 | 3332.94 | 3348.28 | 3355.28 | 17376.23 | 3332.94 | 3348.28 | 5.19 | 5.213
2025-04-01 | Contingency | 221.01 | 222.66 | 211.4 | 3332.94 | 3348.28 | 3355.28 | 17376.23 | 3332.94 | 3348.28 | 5.19 | 5.213
2025-05-01 | Labor | 18245.58 | 17615.98 | 18343.2 | 27768.07 | 27028.33 | 28386.36 | 59898.85 | 27768.07 | 27028.33 | 2.216 | 2.157
2025-05-01 | Software | 1456.66 | 1522.22 | 1553.4 | 27768.07 | 27028.33 | 28386.36 | 59898.85 | 27768.07 | 27028.33 | 2.216 | 2.157
2025-05-01 | Infra | 2755.54 | 2542.17 | 2500.25 | 27768.07 | 27028.33 | 28386.36 | 59898.85 | 27768.07 | 27028.33 | 2.216 | 2.157
2025-05-01 | Travel | 579.8 | 615.69 | 583.66 | 27768.07 | 27028.33 | 28386.36 | 59898.85 | 27768.07 | 27028.33 | 2.216 | 2.157
2025-05-01 | Contingency | 1397.55 | 1374.98 | 1328.77 | 27768.07 | 27028.33 | 28386.36 | 59898.85 | 27768.07 | 27028.33 | 2.216 | 2.157
2025-06-01 | Labor | 31589.15 | 30599.31 | 31712.84 | 68315.61 | 66423.21 | 69691.99 | 73788.85 | 68315.61 | 66423.21 | 1.111 | 1.08
2025-06-01 | Software | 1685.52 | 1536 | 1566.91 | 68315.61 | 66423.21 | 69691.99 | 73788.85 | 68315.61 | 66423.21 | 1.111 | 1.08
2025-06-01 | Infra | 4411.98 | 4415.42 | 4457.27 | 68315.61 | 66423.21 | 69691.99 | 73788.85 | 68315.61 | 66423.21 | 1.111 | 1.08
2025-06-01 | Travel | 1204.54 | 1153.77 | 1194.34 | 68315.61 | 66423.21 | 69691.99 | 73788.85 | 68315.61 | 66423.21 | 1.111 | 1.08
2025-06-01 | Contingency | 1656.34 | 1760.95 | 1688.28 | 68315.61 | 66423.21 | 69691.99 | 73788.85 | 68315.61 | 66423.21 | 1.111 | 1.08
2025-07-01 | Labor | 6006.41 | 6006.64 | 6271.79 | 75818.37 | 73916.75 | 77497.79 | 75818.37 | 75818.37 | 73916.75 | 1.026 | 1
2025-07-01 | Software | 481.57 | 493.71 | 497.23 | 75818.37 | 73916.75 | 77497.79 | 75818.37 | 75818.37 | 73916.75 | 1.026 | 1
2025-07-01 | Infra | 429.39 | 423.14 | 437.81 | 75818.37 | 73916.75 | 77497.79 | 75818.37 | 75818.37 | 73916.75 | 1.026 | 1
2025-07-01 | Travel | 218.68 | 218.49 | 214.61 | 75818.37 | 73916.75 | 77497.79 | 75818.37 | 75818.37 | 73916.75 | 1.026 | 1
2025-07-01 | Contingency | 366.7 | 401.34 | 384.24 | 75818.37 | 73916.75 | 77497.79 | 75818.37 | 75818.37 | 73916.75 | 1.026 | 1

## Milestones
MilestoneID | MilestoneName | PlannedDate | ActualDate | Status | SlippageDays | Owner | Critical
MS-001 | Security Assessment | 2025-03-24 | 2025-03-21 | Completed | -3 | Mipha (7) | FALSE
MS-002 | UAT Start | 2025-04-04 | 2025-04-05 | Completed | 1 | Tingle | FALSE
MS-003 | UAT Complete | 2025-04-15 | 2025-04-13 | Completed | -2 | Zelda | FALSE
MS-004 | Design Complete | 2025-04-26 | 2025-04-22 | Completed | -4 | Tingle | FALSE
MS-005 | Requirements Baseline | 2025-05-07 | 2025-05-08 | Completed | 1 | Rauru | FALSE
MS-006 | Security Assessment | 2025-05-17 | 2025-05-24 | Completed | 7 | Rauru | FALSE
MS-007 | Project Kickoff | 2025-05-28 | 2025-05-26 | Completed | -2 | Zelda | FALSE
MS-008 | Hypercare Complete | 2025-06-08 | 2025-06-06 | Completed | -2 | Link (1) | FALSE
MS-009 | UAT Start | 2025-06-19 | 2025-06-17 | Completed | -2 | Rauru | FALSE
MS-010 | UAT Start | 2025-06-30 | 2025-07-03 | Completed | 3 | Zelda | FALSE

## Risks_Issues_Dependencies
RID_ID | Type | Title | Description | Owner | ImpactArea | Probability_pct | Impact | Severity | ExposureScore | Status | TargetDate | Linkage
RID-001 | Issue | Issue #1 | Synthetic issue description for test purposes. | Zelda | Security |  | Low | Low |  | Mitigated | 2025-07-11 | MS-001
RID-002 | Risk | Risk #2 | Synthetic risk description for test purposes. | Zelda | Security | 57 | High |  | 171 | Mitigated | 2025-03-26 | MS-005
RID-003 | Risk | Risk #3 | Synthetic risk description for test purposes. | Sidon (4) | Cost | 58 | Medium |  | 116 | Open | 2025-04-27 | Vendor-Contract
RID-004 | Risk | Risk #4 | Synthetic risk description for test purposes. | Sidon | Security | 48 | Medium |  | 96 | Closed | 2025-04-22 | External-API
RID-005 | Issue | Issue #5 | Synthetic issue description for test purposes. | Mipha (7) | Quality |  | Medium | Medium |  | Open | 2025-05-05 | Data-Center
RID-006 | Risk | Risk #6 | Synthetic risk description for test purposes. | Tingle | Security | 72 | High |  | 216 | Closed | 2025-03-25 | MS-001
RID-007 | Risk | Risk #7 | Synthetic risk description for test purposes. | Link | Cost | 34 | Medium |  | 68 | Closed | 2025-03-29 | MS-001
RID-008 | Issue | Issue #8 | Synthetic issue description for test purposes. | Zelda | Scope |  | Low | Medium |  | Transferred | 2025-06-07 | External-API
RID-009 | Risk | Risk #9 | Synthetic risk description for test purposes. | Tingle | People | 40 | Medium |  | 80 | Accepted | 2025-05-28 | MS-001
RID-010 | Issue | Issue #10 | Synthetic issue description for test purposes. | Revali | Cost |  | High | High |  | Transferred | 2025-04-03 | Data-Center
RID-011 | Risk | Risk #11 | Synthetic risk description for test purposes. | Rauru | Quality | 39 | Medium |  | 78 | Open | 2025-06-30 | Vendor-Contract
RID-012 | Risk | Risk #12 | Synthetic risk description for test purposes. | Sidon | Scope | 15 | High |  | 45 | Accepted | 2025-06-12 | MS-001
RID-013 | Risk | Risk #13 | Synthetic risk description for test purposes. | Revali | Quality | 6 | Medium |  | 12 | Open | 2025-06-18 | External-API
RID-014 | Issue | Issue #14 | Synthetic issue description for test purposes. | Zelda | Cost |  | Medium | High |  | Transferred | 2025-04-02 | MS-001
RID-015 | Risk | Risk #15 | Synthetic risk description for test purposes. | Rauru | People | 14 | Medium |  | 28 | Transferred | 2025-06-16 | Data-Center
RID-016 | Issue | Issue #16 | Synthetic issue description for test purposes. | Mipha | Scope |  | High | Low |  | Mitigated | 2025-04-16 | External-API
RID-017 | Risk | Risk #17 | Synthetic risk description for test purposes. | Rauru | Quality | 54 | Low |  | 54 | Transferred | 2025-06-15 | Vendor-Contract

## Operational_KPIs
WeekStart | KPI | PlannedValue | ActualValue | Unit | Notes
2025-03-10 | Build Velocity | 50.22 | 46.61 | points
2025-03-10 | Defect Leakage | 11.88 | 12.83 | defects
2025-03-10 | Cycle Time | 5.5 | 6.53 | days
2025-03-10 | MTTR | 4.43 | 4.01 | hours
2025-03-17 | Build Velocity | 53.55 | 51.84 | points
2025-03-17 | Defect Leakage | 9.69 | 12.25 | defects
2025-03-17 | Cycle Time | 4.98 | 5.42 | days
2025-03-17 | MTTR | 4.24 | 3.35 | hours
2025-03-24 | Build Velocity | 59.7 | 59.59 | points
2025-03-24 | Defect Leakage | 5.56 | 6.96 | defects
2025-03-24 | Cycle Time | 5.16 | 5.36 | days
2025-03-24 | MTTR | 9.29 | 6.13 | hours
2025-03-31 | Build Velocity | 44.74 | 47.41 | points
2025-03-31 | Defect Leakage | 9.13 | 5.16 | defects
2025-03-31 | Cycle Time | 3.77 | 3.98 | days
2025-03-31 | MTTR | 9.07 | 10.14 | hours
2025-04-07 | Build Velocity | 32.67 | 30.1 | points
2025-04-07 | Defect Leakage | 2.05 | 1.53 | defects
2025-04-07 | Cycle Time | 4.8 | 4.01 | days
2025-04-07 | MTTR | 5.06 | 3.7 | hours
2025-04-14 | Build Velocity | 37.95 | 38.37 | points
2025-04-14 | Defect Leakage | 6.08 | 3.17 | defects
2025-04-14 | Cycle Time | 4.77 | 3.56 | days
2025-04-14 | MTTR | 8.78 | 7.27 | hours
2025-04-21 | Build Velocity | 35.41 | 33.94 | points
2025-04-21 | Defect Leakage | 5.88 | 3.34 | defects
2025-04-21 | Cycle Time | 7.51 | 8.65 | days
2025-04-21 | MTTR | 11.83 | 11.83 | hours
2025-04-28 | Build Velocity | 26.78 | 26.14 | points
2025-04-28 | Defect Leakage | 3.39 | 2.51 | defects
2025-04-28 | Cycle Time | 5.47 | 4 | days
2025-04-28 | MTTR | 7.48 | 6.69 | hours
2025-05-05 | Build Velocity | 39.37 | 36.04 | points
2025-05-05 | Defect Leakage | 4.52 | 3.15 | defects
2025-05-05 | Cycle Time | 6.13 | 6.11 | days
2025-05-05 | MTTR | 5.56 | 3.76 | hours
2025-05-12 | Build Velocity | 32.19 | 35.08 | points
2025-05-12 | Defect Leakage | 5.32 | 5.3 | defects
2025-05-12 | Cycle Time | 7.02 | 6.07 | days
2025-05-12 | MTTR | 6.68 | 7.82 | hours
2025-05-19 | Build Velocity | 54.38 | 59.54 | points
2025-05-19 | Defect Leakage | 3.36 | 2.54 | defects
2025-05-19 | Cycle Time | 7.74 | 6.19 | days
2025-05-19 | MTTR | 6.51 | 8.31 | hours
2025-05-26 | Build Velocity | 58.75 | 56.3 | points
2025-05-26 | Defect Leakage | 8.95 | 7.99 | defects
2025-05-26 | Cycle Time | 5.88 | 4.83 | days
2025-05-26 | MTTR | 7.01 | 8.21 | hours
2025-06-02 | Build Velocity | 35.72 | 32.96 | points
2025-06-02 | Defect Leakage | 7.64 | 7.44 | defects
2025-06-02 | Cycle Time | 5.73 | 5.96 | days
2025-06-02 | MTTR | 8.4 | 10.64 | hours
2025-06-09 | Build Velocity | 38.46 | 40.07 | points
2025-06-09 | Defect Leakage | 6.38 | 4.68 | defects
2025-06-09 | Cycle Time | 6.46 | 7.17 | days
2025-06-09 | MTTR | 10.37 | 9.19 | hours
2025-06-16 | Build Velocity | 39.97 | 41.04 | points
2025-06-16 | Defect Leakage | 4.42 | 4.54 | defects
2025-06-16 | Cycle Time | 6.58 | 7.2 | days
2025-06-16 | MTTR | 4.59 | 5.94 | hours
2025-06-23 | Build Velocity | 39.17 | 38.39 | points
2025-06-23 | Defect Leakage | 7.07 | 8.74 | defects
2025-06-23 | Cycle Time | 6.46 | 6.28 | days
2025-06-23 | MTTR | 10.33 | 8.79 | hours
2025-06-30 | Build Velocity | 55.82 | 56.23 | points
2025-06-30 | Defect Leakage | 8.38 | 4.76 | defects
2025-06-30 | Cycle Time | 6.84 | 7.04 | days
2025-06-30 | MTTR | 6.84 | 7.2 | hours
2025-07-07 | Build Velocity | 21.77 | 23.88 | points
2025-07-07 | Defect Leakage | 8.77 | 7.19 | defects
2025-07-07 | Cycle Time | 6.76 | 8 | days
2025-07-07 | MTTR | 7.44 | 4.52 | hours

## Data_Dictionary
Sheet | Column | Description
Project_Overview | ProjectID | Global unique project ID
Project_Overview | ProjectName | Fictional project name
Project_Overview | DatasetSet | SetA/SetB/SetC
Project_Overview | ProjectTheme | Fictional universe label
Project_Overview | Sponsor | Fictional sponsor
Project_Overview | ProjectManager | Fictional PM
Project_Overview | Portfolio | Portfolio grouping
Project_Overview | Domain | Solution domain
Project_Overview | DeliveryMethod | Agile/Hybrid/Waterfall
Project_Overview | StartDate | Planned start date
Project_Overview | EndDate | Planned end date
Project_Overview | CurrentPhase | Current phase at time of generation
Project_Overview | HealthRAG | Red/Amber/Green overall health
Project_Overview | Complexity | Low/Medium/High
Project_Overview | RiskProfile | Low/Medium/High
Project_Overview | Maturity | Emerging/Defined/Optimized
Project_Overview | Description | Short description
Resources | ResourceID | Unique resource key
Resources | ResourceName | Fictional name
Resources | Role | Role on project
Resources | SkillTier | Junior/Mid/Senior/Principal
Resources | Location | Fictional/Generic location
Resources | CostRate_USD_per_hour | Internal cost rate ($/hr)
Resources | BillRate_USD_per_hour | External bill rate ($/hr)
Resources | UtilizationTarget_pct | Target utilization %
Resources | AllocationStart | Allocation start date
Resources | AllocationEnd | Allocation end date
Capacity_Effort | Month | First day of month
Capacity_Effort | ResourceID | FK to Resources
Capacity_Effort | Role | Role on project
Capacity_Effort | CapacityHours | Capacity hours in month
Capacity_Effort | PlannedHours | Planned hours
Capacity_Effort | ActualHours | Actual hours
Capacity_Effort | VarianceHours | Actual - Planned
Capacity_Effort | Utilization_pct | Actual/Capacity*100
Budget_Costs | Month | First day of month
Budget_Costs | CostCategory | Labor/Software/Infra/Travel/Contingency
Budget_Costs | PlannedCost_USD | Planned monthly cost
Budget_Costs | ActualCost_USD | Actual monthly cost
Budget_Costs | ForecastCost_USD | Forecast monthly cost
Budget_Costs | CumPlanned_USD | Cumulative planned cost
Budget_Costs | CumActual_USD | Cumulative actual cost
Budget_Costs | CumForecast_USD | Cumulative forecast cost
Budget_Costs | EV | Earned Value (cumulative)
Budget_Costs | PV | Planned Value (cumulative)
Budget_Costs | AC | Actual Cost (cumulative)
Budget_Costs | CPI | EV/AC
Budget_Costs | SPI | EV/PV
Milestones | MilestoneID | Unique milestone ID
Milestones | MilestoneName | Milestone title
Milestones | PlannedDate | Planned completion date
Milestones | ActualDate | Actual completion date (optional)
Milestones | Status | Status string
Milestones | SlippageDays | Actual - Planned (days)
Milestones | Owner | Responsible resource
Milestones | Critical | Critical path flag
Risks_Issues_Dependencies | RID_ID | Unique RID ID
Risks_Issues_Dependencies | Type | Risk/Issue/Dependency
Risks_Issues_Dependencies | Title | Short title
Risks_Issues_Dependencies | Description | Narrative description
Risks_Issues_Dependencies | Owner | Responsible resource
Risks_Issues_Dependencies | ImpactArea | Scope/Cost/Schedule/Quality/People/Security
Risks_Issues_Dependencies | Probability_pct | Probability for Risks (0-100%)
Risks_Issues_Dependencies | Impact | Impact level (Low/Medium/High)
Risks_Issues_Dependencies | Severity | Issue severity (Low/Medium/High)
Risks_Issues_Dependencies | ExposureScore | Risk exposure (prob*impact weight)
Risks_Issues_Dependencies | Status | Open/Mitigated/Closed/Transferred/Accepted
Risks_Issues_Dependencies | TargetDate | Target resolve date
Risks_Issues_Dependencies | Linkage | Related milestone/dependency
Operational_KPIs | WeekStart | Week start date (Monday)
Operational_KPIs | KPI | KPI name
Operational_KPIs | PlannedValue | Planned value
Operational_KPIs | ActualValue | Actual value
Operational_KPIs | Unit | Unit of measure
Operational_KPIs | Notes | Notes