## Project_Overview
ProjectID | ProjectName | DatasetSet | ProjectTheme | Sponsor | ProjectManager | Portfolio | Domain | DeliveryMethod | StartDate | EndDate | CurrentPhase | HealthRAG | Complexity | RiskProfile | Maturity | Description
PRJ-A-004 | Pandora IoT Telemetry Pilot | SetA | Avatar | Grace Augustine | Trudy Chacon | Digital Delivery | IoT | Hybrid | 2026-04-17 | 2027-01-15 | Discovery | Green | Medium | Low | Emerging | Pandora IoT Telemetry Pilot delivering IoT capabilities using Hybrid methods within the Avatar universe.

## Resources
ResourceID | ResourceName | Role | SkillTier | Location | CostRate_USD_per_hour | BillRate_USD_per_hour | UtilizationTarget_pct | AllocationStart | AllocationEnd
R-A-001 | Eytukan | Business Analyst | Junior | Avatar – Remote | 116.1 | 168.76 | 83 | 2026-06-14 | 2026-05-12
R-A-002 | Mo'at | DevOps Engineer | Mid | Avatar – Remote | 145.36 | 225.99 | 89.3 | 2026-08-19 | 2026-07-29
R-A-003 | Grace Augustine | UX Designer | Principal | Avatar – Remote | 99.86 | 143.98 | 82.3 | 2026-11-10 | 2026-08-03
R-A-004 | Jake Sully | Developer | Mid | Avatar – Remote | 122.58 | 175.05 | 84.5 | 2026-11-22 | 2026-11-16
R-A-005 | Trudy Chacon | Project Manager | Junior | Avatar – Remote | 112.89 | 155.25 | 85.8 | 2026-07-21 | 2026-11-04
R-A-006 | Neytiri | Developer | Principal | Avatar – Remote | 106.6 | 145.84 | 85.3 | 2026-09-24 | 2026-11-15
R-A-007 | Quaritch | Architect | Principal | Avatar – Remote | 182.83 | 257.16 | 86.2 | 2026-09-16 | 2026-06-13
R-A-008 | Norm Spellman | Data Engineer | Junior | Avatar – Remote | 121.92 | 165.49 | 81.8 | 2026-06-28 | 2026-11-15
R-A-009 | Neytiri (8) | QA Engineer | Mid | Avatar – Remote | 68.27 | 97.13 | 84.9 | 2026-07-14 | 2026-07-25
R-A-010 | Neytiri (9) | QA Engineer | Principal | Avatar – Remote | 68.42 | 95.21 | 86.2 | 2026-10-17 | 2026-05-05
R-A-011 | Mo'at (10) | QA Engineer | Principal | Avatar – Remote | 71.71 | 102.03 | 84.1 | 2026-12-24 | 2026-11-29
R-A-012 | Grace Augustine (11) | Data Engineer | Junior | Avatar – Remote | 131.07 | 173.7 | 88 | 2026-08-07 | 2026-09-27
R-A-013 | Quaritch (12) | Project Manager | Principal | Avatar – Remote | 113.49 | 156.61 | 85.7 | 2026-12-26 | 2026-06-27
R-A-014 | Grace Augustine (13) | UX Designer | Senior | Avatar – Remote | 96.07 | 143.57 | 85.4 | 2026-05-08 | 2026-12-12
R-A-015 | Trudy Chacon (14) | QA Engineer | Mid | Avatar – Remote | 119.39 | 154.74 | 83 | 2026-05-03 | 2026-12-17
R-A-016 | Tsu'Tey | Developer | Junior | Avatar – Remote | 138.98 | 179.17 | 87.8 | 2026-08-16 | 2026-08-16
R-A-017 | Eytukan (16) | Data Engineer | Principal | Avatar – Remote | 141.15 | 198.71 | 81.7 | 2026-06-27 | 2026-08-14
R-A-018 | Trudy Chacon (17) | Data Engineer | Senior | Avatar – Remote | 156.38 | 235.59 | 86 | 2026-07-12 | 2026-10-13
R-A-019 | Grace Augustine (18) | Data Engineer | Junior | Avatar – Remote | 140.09 | 235.15 | 81.4 | 2026-11-13 | 2026-05-31
R-A-020 | Trudy Chacon (19) | Data Scientist | Mid | Avatar – Remote | 128.88 | 211.33 | 81.5 | 2026-09-28 | 2026-09-04

## Capacity_Effort
Month | ResourceID | Role | CapacityHours | PlannedHours | ActualHours | VarianceHours | Utilization_pct
2026-05-01 | R-A-014 | UX Designer | 128 | 112.2 | 111.9 | -0.2 | 87.4
2026-05-01 | R-A-015 | QA Engineer | 160 | 133.8 | 131.5 | -2.3 | 82.2
2026-06-01 | R-A-008 | Data Engineer | 16 | 13 | 14 | 1 | 87.6
2026-06-01 | R-A-014 | UX Designer | 176 | 144.2 | 137.8 | -6.4 | 78.3
2026-06-01 | R-A-015 | QA Engineer | 176 | 152.5 | 166.2 | 13.7 | 94.4
2026-06-01 | R-A-017 | Data Engineer | 16 | 12.8
2026-07-01 | R-A-005 | Project Manager | 72 | 63.5 | 66.4 | 2.9 | 92.2
2026-07-01 | R-A-008 | Data Engineer | 184 | 149.9 | 145.6 | -4.3 | 79.2
2026-07-01 | R-A-009 | QA Engineer | 72 | 58.5 | 55.2 | -3.3 | 76.6
2026-07-01 | R-A-014 | UX Designer | 184 | 156 | 148.8 | -7.2 | 80.9
2026-07-01 | R-A-015 | QA Engineer | 184 | 157.7 | 160.2 | 2.5 | 87.1
2026-07-01 | R-A-017 | Data Engineer | 184 | 151.3 | 146.6 | -4.7 | 79.7
2026-07-01 | R-A-018 | Data Engineer | 120 | 105.1 | 96.7 | -8.4 | 80.6
2026-08-01 | R-A-005 | Project Manager | 168 | 148.2 | 137.1 | -11.1 | 81.6
2026-08-01 | R-A-008 | Data Engineer | 168 | 142.3 | 128.1 | -14.2 | 76.3
2026-08-01 | R-A-012 | Data Engineer | 136 | 125.2 | 129.9 | 4.7 | 95.5
2026-08-01 | R-A-014 | UX Designer | 168 | 138.2 | 128.8 | -9.4 | 76.6
2026-08-01 | R-A-015 | QA Engineer | 168 | 145.5 | 150 | 4.5 | 89.3
2026-08-01 | R-A-016 | Developer | 0 | 0 | 0 | 0
2026-08-01 | R-A-017 | Data Engineer | 80 | 63.2 | 60.7 | -2.5 | 75.9
2026-08-01 | R-A-018 | Data Engineer | 168 | 147.4 | 151.9 | 4.6 | 90.4
2026-09-01 | R-A-005 | Project Manager | 176 | 154.1
2026-09-01 | R-A-006 | Developer | 40 | 34 | 32.2 | -1.9 | 80.4
2026-09-01 | R-A-008 | Data Engineer | 176 | 146.6
2026-09-01 | R-A-012 | Data Engineer | 152 | 136.4 | 149.7 | 13.3 | 98.5
2026-09-01 | R-A-014 | UX Designer | 176 | 149.1 | 136.3 | -12.8 | 77.5
2026-09-01 | R-A-015 | QA Engineer | 176 | 144.4 | 132.9 | -11.5 | 75.5
2026-09-01 | R-A-018 | Data Engineer | 176 | 148.5 | 137.8 | -10.8 | 78.3
2026-10-01 | R-A-005 | Project Manager | 176 | 155.1 | 143.8 | -11.4 | 81.7
2026-10-01 | R-A-006 | Developer | 176 | 157.5 | 158.5 | 1 | 90.1
2026-10-01 | R-A-008 | Data Engineer | 176 | 136.9 | 135.3 | -1.6 | 76.8
2026-10-01 | R-A-014 | UX Designer | 176 | 153.6 | 142.9 | -10.7 | 81.2
2026-10-01 | R-A-015 | QA Engineer | 176 | 144.8 | 155.2 | 10.4 | 88.2
2026-10-01 | R-A-018 | Data Engineer | 72 | 59.4 | 62.4 | 3 | 86.6
2026-11-01 | R-A-005 | Project Manager | 24 | 20.8 | 22.7 | 1.9 | 94.6
2026-11-01 | R-A-006 | Developer | 80 | 67 | 64 | -3 | 80
2026-11-01 | R-A-008 | Data Engineer | 80 | 62.7 | 64 | 1.3 | 80
2026-11-01 | R-A-014 | UX Designer | 168 | 145 | 150.5 | 5.5 | 89.6
2026-11-01 | R-A-015 | QA Engineer | 168 | 144.3 | 138.6 | -5.7 | 82.5
2026-12-01 | R-A-014 | UX Designer | 72 | 61.6 | 64.7 | 3.1 | 89.8
2026-12-01 | R-A-015 | QA Engineer | 104 | 84.6 | 91.3 | 6.7 | 87.8

## Budget_Costs
Month | CostCategory | PlannedCost_USD | ActualCost_USD | ForecastCost_USD | CumPlanned_USD | CumActual_USD | CumForecast_USD | EV | PV | AC | CPI | SPI
2026-04-01 | Labor | 0 | 0 | 0 | 0 | 0 | 0 | 6183.63 | 0 | 0
2026-04-01 | Software | 0 | 0 | 0 | 0 | 0 | 0 | 6183.63 | 0 | 0
2026-04-01 | Infra | 0 | 0 | 0 | 0 | 0 | 0 | 6183.63 | 0 | 0
2026-04-01 | Travel | 0 | 0 | 0 | 0 | 0 | 0 | 6183.63 | 0 | 0
2026-04-01 | Contingency | 0 | 0 | 0 | 0 | 0 | 0 | 6183.63 | 0 | 0
2026-05-01 | Labor | 26753.44 | 26450.02 | 26066.28 | 33015.77 | 32713.14 | 33496.82 | 19896.1 | 33015.77 | 32713.14 | 0.608 | 0.603
2026-05-01 | Software | 2039.11 | 1868.81 | 1939.12 | 33015.77 | 32713.14 | 33496.82 | 19896.1 | 33015.77 | 32713.14 | 0.608 | 0.603
2026-05-01 | Infra | 1497.5 | 1508.45 | 1459.43 | 33015.77 | 32713.14 | 33496.82 | 19896.1 | 33015.77 | 32713.14 | 0.608 | 0.603
2026-05-01 | Travel | 332.24 | 339.96 | 347.25 | 33015.77 | 32713.14 | 33496.82 | 19896.1 | 33015.77 | 32713.14 | 0.608 | 0.603
2026-05-01 | Contingency | 2393.48 | 2286.96 | 2338.04 | 33015.77 | 32713.14 | 33496.82 | 19896.1 | 33015.77 | 32713.14 | 0.608 | 0.603
2026-06-01 | Labor | 35451.95 | 36555.18 | 36986.74 | 81909.55 | 83079.96 | 81214.69 | 58211.98 | 81909.55 | 83079.96 | 0.701 | 0.711
2026-06-01 | Software | 4021.29 | 3968.6 | 4085.69 | 81909.55 | 83079.96 | 81214.69 | 58211.98 | 81909.55 | 83079.96 | 0.701 | 0.711
2026-06-01 | Infra | 6210.44 | 6152.52 | 5940.67 | 81909.55 | 83079.96 | 81214.69 | 58211.98 | 81909.55 | 83079.96 | 0.701 | 0.711
2026-06-01 | Travel | 1320.31 | 1349.05 | 1365.36 | 81909.55 | 83079.96 | 81214.69 | 58211.98 | 81909.55 | 83079.96 | 0.701 | 0.711
2026-06-01 | Contingency | 1889.79 | 1817.71 | 1883.75 | 81909.55 | 83079.96 | 81214.69 | 58211.98 | 81909.55 | 83079.96 | 0.701 | 0.711
2026-07-01 | Labor | 101044.37 | 98251.98 | 97103.13 | 221290.69 | 218939.61 | 215308.81 | 175518.17 | 221290.69 | 218939.61 | 0.802 | 0.793
2026-07-01 | Software | 6707.66 | 7226.04 | 6712.58 | 221290.69 | 218939.61 | 215308.81 | 175518.17 | 221290.69 | 218939.61 | 0.802 | 0.793
2026-07-01 | Infra | 19496.76 | 20555.16 | 20559.24 | 221290.69 | 218939.61 | 215308.81 | 175518.17 | 221290.69 | 218939.61 | 0.802 | 0.793
2026-07-01 | Travel | 3124.31 | 2830.23 | 2970.46 | 221290.69 | 218939.61 | 215308.81 | 175518.17 | 221290.69 | 218939.61 | 0.802 | 0.793
2026-07-01 | Contingency | 9008.04 | 9561.33 | 8945 | 221290.69 | 218939.61 | 215308.81 | 175518.17 | 221290.69 | 218939.61 | 0.802 | 0.793
2026-08-01 | Labor | 113108.69 | 110725.41 | 108825.9 | 369221.82 | 363486.96 | 364460.03 | 360490.87 | 369221.82 | 363486.96 | 0.992 | 0.976
2026-08-01 | Software | 10804.12 | 10217.25 | 10422.48 | 369221.82 | 363486.96 | 364460.03 | 360490.87 | 369221.82 | 363486.96 | 0.992 | 0.976
2026-08-01 | Infra | 11765.41 | 11786.17 | 11640.04 | 369221.82 | 363486.96 | 364460.03 | 360490.87 | 369221.82 | 363486.96 | 0.992 | 0.976
2026-08-01 | Travel | 3391.5 | 3082.22 | 3093.75 | 369221.82 | 363486.96 | 364460.03 | 360490.87 | 369221.82 | 363486.96 | 0.992 | 0.976
2026-08-01 | Contingency | 8861.42 | 9504.63 | 9646.06 | 369221.82 | 363486.96 | 364460.03 | 360490.87 | 369221.82 | 363486.96 | 0.992 | 0.976
2026-09-01 | Labor | 111558.55 | 110266.72 | 116116.72 | 524886.11 | 517627.94 | 517242.03 | 540753.88 | 524886.11 | 517627.94 | 1.045 | 1.03
2026-09-01 | Software | 15773.8 | 15780.23 | 16494.09 | 524886.11 | 517627.94 | 517242.03 | 540753.88 | 524886.11 | 517627.94 | 1.045 | 1.03
2026-09-01 | Infra | 17972.07 | 19416.81 | 18026.82 | 524886.11 | 517627.94 | 517242.03 | 540753.88 | 524886.11 | 517627.94 | 1.045 | 1.03
2026-09-01 | Travel | 2986.95 | 2795.4 | 2862 | 524886.11 | 517627.94 | 517242.03 | 540753.88 | 524886.11 | 517627.94 | 1.045 | 1.03
2026-09-01 | Contingency | 7372.92 | 7821.69 | 7475.81 | 524886.11 | 517627.94 | 517242.03 | 540753.88 | 524886.11 | 517627.94 | 1.045 | 1.03
2026-10-01 | Labor | 92322.58 | 91641.3 | 95594.44 | 646392.03 | 637823.94 | 637526.52 | 655663.55 | 646392.03 | 637823.94 | 1.028 | 1.014
2026-10-01 | Software | 12415.97 | 12643.66 | 12879.55 | 646392.03 | 637823.94 | 637526.52 | 655663.55 | 646392.03 | 637823.94 | 1.028 | 1.014
2026-10-01 | Infra | 9148.72 | 9136.57 | 8908.44 | 646392.03 | 637823.94 | 637526.52 | 655663.55 | 646392.03 | 637823.94 | 1.028 | 1.014
2026-10-01 | Travel | 2965.74 | 3127.44 | 2911.57 | 646392.03 | 637823.94 | 637526.52 | 655663.55 | 646392.03 | 637823.94 | 1.028 | 1.014
2026-10-01 | Contingency | 4652.92 | 4369.48 | 4442.53 | 646392.03 | 637823.94 | 637526.52 | 655663.55 | 646392.03 | 637823.94 | 1.028 | 1.014
2026-11-01 | Labor | 48292.82 | 48193.87 | 46110.67 | 709786.32 | 701330.2 | 702429.94 | 703801.64 | 709786.32 | 701330.2 | 1.004 | 0.992
2026-11-01 | Software | 3539.85 | 3259.46 | 3539.17 | 709786.32 | 701330.2 | 702429.94 | 703801.64 | 709786.32 | 701330.2 | 1.004 | 0.992
2026-11-01 | Infra | 4924.11 | 4953.47 | 5046.32 | 709786.32 | 701330.2 | 702429.94 | 703801.64 | 709786.32 | 701330.2 | 1.004 | 0.992
2026-11-01 | Travel | 2104.74 | 1994.53 | 1955.65 | 709786.32 | 701330.2 | 702429.94 | 703801.64 | 709786.32 | 701330.2 | 1.004 | 0.992
2026-11-01 | Contingency | 4532.76 | 4525.53 | 4719.2 | 709786.32 | 701330.2 | 702429.94 | 703801.64 | 709786.32 | 701330.2 | 1.004 | 0.992
2026-12-01 | Labor | 16018.31 | 17116.04 | 16237.96 | 731801.1 | 724355.12 | 725774.58 | 728606.23 | 731801.1 | 724355.12 | 1.006 | 0.996
2026-12-01 | Software | 2238.22 | 2047.89 | 2073.26 | 731801.1 | 724355.12 | 725774.58 | 728606.23 | 731801.1 | 724355.12 | 1.006 | 0.996
2026-12-01 | Infra | 2049.76 | 2077.57 | 2028.22 | 731801.1 | 724355.12 | 725774.58 | 728606.23 | 731801.1 | 724355.12 | 1.006 | 0.996
2026-12-01 | Travel | 609.24 | 601.32 | 622.67 | 731801.1 | 724355.12 | 725774.58 | 728606.23 | 731801.1 | 724355.12 | 1.006 | 0.996
2026-12-01 | Contingency | 1099.25 | 1201.31 | 1183.78 | 731801.1 | 724355.12 | 725774.58 | 728606.23 | 731801.1 | 724355.12 | 1.006 | 0.996
2027-01-01 | Labor | 0 | 0 | 0 | 731801.1 | 724355.12 | 725774.58 | 731801.1 | 731801.1 | 724355.12 | 1.01 | 1
2027-01-01 | Software | 0 | 0 | 0 | 731801.1 | 724355.12 | 725774.58 | 731801.1 | 731801.1 | 724355.12 | 1.01 | 1
2027-01-01 | Infra | 0 | 0 | 0 | 731801.1 | 724355.12 | 725774.58 | 731801.1 | 731801.1 | 724355.12 | 1.01 | 1
2027-01-01 | Travel | 0 | 0 | 0 | 731801.1 | 724355.12 | 725774.58 | 731801.1 | 731801.1 | 724355.12 | 1.01 | 1
2027-01-01 | Contingency | 0 | 0 | 0 | 731801.1 | 724355.12 | 725774.58 | 731801.1 | 731801.1 | 724355.12 | 1.01 | 1

## Milestones
MilestoneID | MilestoneName | PlannedDate | ActualDate | Status | SlippageDays | Owner | Critical
MS-001 | UAT Complete | 2026-05-11 | 2026-05-08 | Not Started | -3 | Eytukan | FALSE
MS-002 | Requirements Baseline | 2026-06-05 | 2026-06-08 | Not Started | 3 | Norm Spellman | TRUE
MS-003 | Hypercare Complete | 2026-06-30 | 2026-06-27 | Not Started | -3 | Jake Sully | TRUE
MS-004 | System Integration | 2026-07-25 | 2026-07-22 | Not Started | -3 | Quaritch | FALSE
MS-005 | MVP Build | 2026-08-19 | 2026-08-24 | Not Started | 5 | Grace Augustine | FALSE
MS-006 | Design Complete | 2026-09-12 | 2026-09-08 | Not Started | -4 | Eytukan | FALSE
MS-007 | Hypercare Complete | 2026-10-07 | 2026-10-09 | Not Started | 2 | Trudy Chacon | TRUE
MS-008 | Performance Test | 2026-11-01 | 2026-10-27 | Not Started | -5 | Trudy Chacon (14) | TRUE
MS-009 | UAT Start | 2026-11-26 | 2026-12-02 | Not Started | 6 | Quaritch (12) | FALSE
MS-010 | Architecture Review | 2026-12-21 | 2026-12-18 | Not Started | -3 | Grace Augustine (11) | TRUE

## Risks_Issues_Dependencies
RID_ID | Type | Title | Description | Owner | ImpactArea | Probability_pct | Impact | Severity | ExposureScore | Status | TargetDate | Linkage
RID-001 | Risk | Risk #1 | Synthetic risk description for test purposes. | Trudy Chacon | Quality | 36 | Low |  | 36 | Mitigated | 2026-09-22 | Data-Center
RID-002 | Risk | Risk #2 | Synthetic risk description for test purposes. | Neytiri (8) | Scope | 72 | Low |  | 72 | Mitigated | 2026-08-29 | Data-Center
RID-003 | Dependency | Dependency #3 | Synthetic dependency description for test purposes. | Grace Augustine (11) | Schedule |  | Medium |  |  | Transferred | 2026-10-17 | Data-Center
RID-004 | Risk | Risk #4 | Synthetic risk description for test purposes. | Neytiri | People | 8 | Low |  | 8 | Open | 2026-09-14 | External-API
RID-005 | Risk | Risk #5 | Synthetic risk description for test purposes. | Grace Augustine (18) | People | 17 | High |  | 51 | Closed | 2026-08-28 | Vendor-Contract
RID-006 | Issue | Issue #6 | Synthetic issue description for test purposes. | Mo'at | Cost |  | Medium | High |  | Open | 2026-11-08 | MS-005
RID-007 | Risk | Risk #7 | Synthetic risk description for test purposes. | Mo'at (10) | People | 80 | High |  | 240 | Closed | 2026-05-08 | Vendor-Contract
RID-008 | Issue | Issue #8 | Synthetic issue description for test purposes. | Grace Augustine (18) | Quality |  | High | High |  | Mitigated | 2027-01-01 | MS-005
RID-009 | Risk | Risk #9 | Synthetic risk description for test purposes. | Mo'at | Cost | 72 | Low |  | 72 | Open | 2026-12-24 | Data-Center
RID-010 | Issue | Issue #10 | Synthetic issue description for test purposes. | Mo'at (10) | People |  | Medium | High |  | Open | 2026-10-06 | MS-005
RID-011 | Issue | Issue #11 | Synthetic issue description for test purposes. | Trudy Chacon | Security |  | Medium | High |  | Accepted | 2026-10-27 | Vendor-Contract
RID-012 | Dependency | Dependency #12 | Synthetic dependency description for test purposes. | Quaritch (12) | Security |  | Medium |  |  | Open | 2026-10-06 | MS-005
RID-013 | Dependency | Dependency #13 | Synthetic dependency description for test purposes. | Tsu'Tey | Cost |  | Medium |  |  | Open | 2026-10-23 | Data-Center
RID-014 | Risk | Risk #14 | Synthetic risk description for test purposes. | Neytiri (9) | Scope | 78 | Low |  | 78 | Transferred | 2026-11-10 | Data-Center

## Operational_KPIs
WeekStart | KPI | PlannedValue | ActualValue | Unit | Notes
2026-04-13 | Build Velocity | 27.28 | 26.29 | points
2026-04-13 | Defect Leakage | 10.09 | 9.98 | defects
2026-04-13 | Cycle Time | 6.2 | 4.66 | days
2026-04-13 | MTTR | 7.97 | 6.63 | hours
2026-04-20 | Build Velocity | 23.11 | 22.4 | points
2026-04-20 | Defect Leakage | 5.2 | 5.24 | defects
2026-04-20 | Cycle Time | 7.82 | 8.68 | days
2026-04-20 | MTTR | 9.36 | 10.39 | hours
2026-04-27 | Build Velocity | 33.43 | 30.16 | points
2026-04-27 | Defect Leakage | 4.1 | 4.32 | defects
2026-04-27 | Cycle Time | 4.75 | 5.2 | days
2026-04-27 | MTTR | 9.76 | 6.19 | hours
2026-05-04 | Build Velocity | 37.53 | 36.93 | points
2026-05-04 | Defect Leakage | 3.66 | 3.05 | defects
2026-05-04 | Cycle Time | 7.41 | 6.49 | days
2026-05-04 | MTTR | 7 | 8.26 | hours
2026-05-11 | Build Velocity | 51.55 | 52.35 | points
2026-05-11 | Defect Leakage | 9.58 | 6.52 | defects
2026-05-11 | Cycle Time | 5.26 | 5.78 | days
2026-05-11 | MTTR | 4.27 | 2.62 | hours
2026-05-18 | Build Velocity | 30.45 | 28.04 | points
2026-05-18 | Defect Leakage | 5.42 | 6.56 | defects
2026-05-18 | Cycle Time | 3.8 | 2.81 | days
2026-05-18 | MTTR | 11.53 | 14.82 | hours
2026-05-25 | Build Velocity | 33.52 | 36.77 | points
2026-05-25 | Defect Leakage | 10.93 | 11.63 | defects
2026-05-25 | Cycle Time | 5.16 | 5.29 | days
2026-05-25 | MTTR | 8.86 | 8.01 | hours
2026-06-01 | Build Velocity | 22.14 | 21.39 | points
2026-06-01 | Defect Leakage | 11.74 | 9.72 | defects
2026-06-01 | Cycle Time | 5.77 | 6.71 | days
2026-06-01 | MTTR | 8.32 | 8.84 | hours
2026-06-08 | Build Velocity | 31.9 | 29.32 | points
2026-06-08 | Defect Leakage | 5.93 | 5.57 | defects
2026-06-08 | Cycle Time | 5.45 | 3.97 | days
2026-06-08 | MTTR | 4.03 | 2.67 | hours
2026-06-15 | Build Velocity | 52.96 | 54.28 | points
2026-06-15 | Defect Leakage | 6.8 | 3.93 | defects
2026-06-15 | Cycle Time | 4.03 | 4.11 | days
2026-06-15 | MTTR | 11.82 | 11.01 | hours
2026-06-22 | Build Velocity | 24.62 | 26.02 | points
2026-06-22 | Defect Leakage | 6.71 | 8.16 | defects
2026-06-22 | Cycle Time | 4.33 | 4.42 | days
2026-06-22 | MTTR | 7.1 | 6.1 | hours
2026-06-29 | Build Velocity | 35.26 | 33.05 | points
2026-06-29 | Defect Leakage | 2.45 | 2.08 | defects
2026-06-29 | Cycle Time | 4.32 | 4.83 | days
2026-06-29 | MTTR | 8.51 | 6.01 | hours
2026-07-06 | Build Velocity | 47.86 | 44 | points
2026-07-06 | Defect Leakage | 8.68 | 9.95 | defects
2026-07-06 | Cycle Time | 5.07 | 5.47 | days
2026-07-06 | MTTR | 5.82 | 3.74 | hours
2026-07-13 | Build Velocity | 35.48 | 35.64 | points
2026-07-13 | Defect Leakage | 11.66 | 12.24 | defects
2026-07-13 | Cycle Time | 7.68 | 7.58 | days
2026-07-13 | MTTR | 5.89 | 4.76 | hours
2026-07-20 | Build Velocity | 35.79 | 38.33 | points
2026-07-20 | Defect Leakage | 2.35 | 2.25 | defects
2026-07-20 | Cycle Time | 5.58 | 5.5 | days
2026-07-20 | MTTR | 11.86 | 8.34 | hours
2026-07-27 | Build Velocity | 57.97 | 57.38 | points
2026-07-27 | Defect Leakage | 11.49 | 7.28 | defects
2026-07-27 | Cycle Time | 4.06 | 3.23 | days
2026-07-27 | MTTR | 4.34 | 2.84 | hours
2026-08-03 | Build Velocity | 47.33 | 44.5 | points
2026-08-03 | Defect Leakage | 10.23 | 6.32 | defects
2026-08-03 | Cycle Time | 5.98 | 5.14 | days
2026-08-03 | MTTR | 9.82 | 11.44 | hours
2026-08-10 | Build Velocity | 23.48 | 23.75 | points
2026-08-10 | Defect Leakage | 7.52 | 8.91 | defects
2026-08-10 | Cycle Time | 5.6 | 6.49 | days
2026-08-10 | MTTR | 4.1 | 4.47 | hours
2026-08-17 | Build Velocity | 43.5 | 45.95 | points
2026-08-17 | Defect Leakage | 3.13 | 1.94 | defects
2026-08-17 | Cycle Time | 5.83 | 5.78 | days
2026-08-17 | MTTR | 11.72 | 7.85 | hours
2026-08-24 | Build Velocity | 24.23 | 25.58 | points
2026-08-24 | Defect Leakage | 9.86 | 11.77 | defects
2026-08-24 | Cycle Time | 7.4 | 8.43 | days
2026-08-24 | MTTR | 6.11 | 6.47 | hours
2026-08-31 | Build Velocity | 42.88 | 42.65 | points
2026-08-31 | Defect Leakage | 3.72 | 3.06 | defects
2026-08-31 | Cycle Time | 6.09 | 6.34 | days
2026-08-31 | MTTR | 7.21 | 6.33 | hours
2026-09-07 | Build Velocity | 55.16 | 57.26 | points
2026-09-07 | Defect Leakage | 2.49 | 2.19 | defects
2026-09-07 | Cycle Time | 4.34 | 3.85 | days
2026-09-07 | MTTR | 6.7 | 7.75 | hours
2026-09-14 | Build Velocity | 32.44 | 34.66 | points
2026-09-14 | Defect Leakage | 10.58 | 11.09 | defects
2026-09-14 | Cycle Time | 7.86 | 6.4 | days
2026-09-14 | MTTR | 6.4 | 7.18 | hours
2026-09-21 | Build Velocity | 50.96 | 49.14 | points
2026-09-21 | Defect Leakage | 9.29 | 9.14 | defects
2026-09-21 | Cycle Time | 3.45 | 3.17 | days
2026-09-21 | MTTR | 11.31 | 10.01 | hours
2026-09-28 | Build Velocity | 39.38 | 39.51 | points
2026-09-28 | Defect Leakage | 5.74 | 3.13 | defects
2026-09-28 | Cycle Time | 6.96 | 5.1 | days
2026-09-28 | MTTR | 9.68 | 8.54 | hours
2026-10-05 | Build Velocity | 51.22 | 51.47 | points
2026-10-05 | Defect Leakage | 7.69 | 4.91 | defects
2026-10-05 | Cycle Time | 7.38 | 5.9 | days
2026-10-05 | MTTR | 4.46 | 2.78 | hours
2026-10-12 | Build Velocity | 22.02 | 21.41 | points
2026-10-12 | Defect Leakage | 3.99 | 3.17 | defects
2026-10-12 | Cycle Time | 5.32 | 4.78 | days
2026-10-12 | MTTR | 11.38 | 12.26 | hours
2026-10-19 | Build Velocity | 29.68 | 29.61 | points
2026-10-19 | Defect Leakage | 6.46 | 8.2 | defects
2026-10-19 | Cycle Time | 5.37 | 5.24 | days
2026-10-19 | MTTR | 6.75 | 8.01 | hours
2026-10-26 | Build Velocity | 30.35 | 32.35 | points
2026-10-26 | Defect Leakage | 2.9 | 1.52 | defects
2026-10-26 | Cycle Time | 3.25 | 3.66 | days
2026-10-26 | MTTR | 10.24 | 7.68 | hours
2026-11-02 | Build Velocity | 28.85 | 27.27 | points
2026-11-02 | Defect Leakage | 4.07 | 4.15 | defects
2026-11-02 | Cycle Time | 5.57 | 6.3 | days
2026-11-02 | MTTR | 11.74 | 12.65 | hours
2026-11-09 | Build Velocity | 38.96 | 36.1 | points
2026-11-09 | Defect Leakage | 3.73 | 4.26 | defects
2026-11-09 | Cycle Time | 4.12 | 4.14 | days
2026-11-09 | MTTR | 11.54 | 12.69 | hours
2026-11-16 | Build Velocity | 48.37 | 46.2 | points
2026-11-16 | Defect Leakage | 10.95 | 12.94 | defects
2026-11-16 | Cycle Time | 5.29 | 4.28 | days
2026-11-16 | MTTR | 6.42 | 6.19 | hours
2026-11-23 | Build Velocity | 44.94 | 45.7 | points
2026-11-23 | Defect Leakage | 2.07 | 2.69 | defects
2026-11-23 | Cycle Time | 7.83 | 8.77 | days
2026-11-23 | MTTR | 8.49 | 8.62 | hours
2026-11-30 | Build Velocity | 31.31 | 32.46 | points
2026-11-30 | Defect Leakage | 6.82 | 5.24 | defects
2026-11-30 | Cycle Time | 4.38 | 3.78 | days
2026-11-30 | MTTR | 6.22 | 6.58 | hours
2026-12-07 | Build Velocity | 58.09 | 59.85 | points
2026-12-07 | Defect Leakage | 3.88 | 3.55 | defects
2026-12-07 | Cycle Time | 4.2 | 3.06 | days
2026-12-07 | MTTR | 10.86 | 12.67 | hours
2026-12-14 | Build Velocity | 36.16 | 34.86 | points
2026-12-14 | Defect Leakage | 3.4 | 1.77 | defects
2026-12-14 | Cycle Time | 5.49 | 4.65 | days
2026-12-14 | MTTR | 11.26 | 9.94 | hours
2026-12-21 | Build Velocity | 49.47 | 50.29 | points
2026-12-21 | Defect Leakage | 11.95 | 13.77 | defects
2026-12-21 | Cycle Time | 4.72 | 4.98 | days
2026-12-21 | MTTR | 9.49 | 9.93 | hours
2026-12-28 | Build Velocity | 39.03 | 42.47 | points
2026-12-28 | Defect Leakage | 5.58 | 4.13 | defects
2026-12-28 | Cycle Time | 3.85 | 3.96 | days
2026-12-28 | MTTR | 8.47 | 6.82 | hours
2027-01-04 | Build Velocity | 38.83 | 40.7 | points
2027-01-04 | Defect Leakage | 9.25 | 8.76 | defects
2027-01-04 | Cycle Time | 7.56 | 8.88 | days
2027-01-04 | MTTR | 11.2 | 11.85 | hours
2027-01-11 | Build Velocity | 28.89 | 27.29 | points
2027-01-11 | Defect Leakage | 10.71 | 8.96 | defects
2027-01-11 | Cycle Time | 7.43 | 6.59 | days
2027-01-11 | MTTR | 8.68 | 8.03 | hours

## Data_Dictionary
Sheet | Column | Description
Project_Overview | ProjectID | Global unique project ID
Project_Overview | ProjectName | Fictional project name
Project_Overview | DatasetSet | SetA/SetB/SetC
Project_Overview | ProjectTheme | Fictional universe label
Project_Overview | Sponsor | Fictional sponsor
Project_Overview | ProjectManager | Fictional PM
Project_Overview | Portfolio | Portfolio grouping
Project_Overview | Domain | Solution domain
Project_Overview | DeliveryMethod | Agile/Hybrid/Waterfall
Project_Overview | StartDate | Planned start date
Project_Overview | EndDate | Planned end date
Project_Overview | CurrentPhase | Current phase at time of generation
Project_Overview | HealthRAG | Red/Amber/Green overall health
Project_Overview | Complexity | Low/Medium/High
Project_Overview | RiskProfile | Low/Medium/High
Project_Overview | Maturity | Emerging/Defined/Optimized
Project_Overview | Description | Short description
Resources | ResourceID | Unique resource key
Resources | ResourceName | Fictional name
Resources | Role | Role on project
Resources | SkillTier | Junior/Mid/Senior/Principal
Resources | Location | Fictional/Generic location
Resources | CostRate_USD_per_hour | Internal cost rate ($/hr)
Resources | BillRate_USD_per_hour | External bill rate ($/hr)
Resources | UtilizationTarget_pct | Target utilization %
Resources | AllocationStart | Allocation start date
Resources | AllocationEnd | Allocation end date
Capacity_Effort | Month | First day of month
Capacity_Effort | ResourceID | FK to Resources
Capacity_Effort | Role | Role on project
Capacity_Effort | CapacityHours | Capacity hours in month
Capacity_Effort | PlannedHours | Planned hours
Capacity_Effort | ActualHours | Actual hours
Capacity_Effort | VarianceHours | Actual - Planned
Capacity_Effort | Utilization_pct | Actual/Capacity*100
Budget_Costs | Month | First day of month
Budget_Costs | CostCategory | Labor/Software/Infra/Travel/Contingency
Budget_Costs | PlannedCost_USD | Planned monthly cost
Budget_Costs | ActualCost_USD | Actual monthly cost
Budget_Costs | ForecastCost_USD | Forecast monthly cost
Budget_Costs | CumPlanned_USD | Cumulative planned cost
Budget_Costs | CumActual_USD | Cumulative actual cost
Budget_Costs | CumForecast_USD | Cumulative forecast cost
Budget_Costs | EV | Earned Value (cumulative)
Budget_Costs | PV | Planned Value (cumulative)
Budget_Costs | AC | Actual Cost (cumulative)
Budget_Costs | CPI | EV/AC
Budget_Costs | SPI | EV/PV
Milestones | MilestoneID | Unique milestone ID
Milestones | MilestoneName | Milestone title
Milestones | PlannedDate | Planned completion date
Milestones | ActualDate | Actual completion date (optional)
Milestones | Status | Status string
Milestones | SlippageDays | Actual - Planned (days)
Milestones | Owner | Responsible resource
Milestones | Critical | Critical path flag
Risks_Issues_Dependencies | RID_ID | Unique RID ID
Risks_Issues_Dependencies | Type | Risk/Issue/Dependency
Risks_Issues_Dependencies | Title | Short title
Risks_Issues_Dependencies | Description | Narrative description
Risks_Issues_Dependencies | Owner | Responsible resource
Risks_Issues_Dependencies | ImpactArea | Scope/Cost/Schedule/Quality/People/Security
Risks_Issues_Dependencies | Probability_pct | Probability for Risks (0-100%)
Risks_Issues_Dependencies | Impact | Impact level (Low/Medium/High)
Risks_Issues_Dependencies | Severity | Issue severity (Low/Medium/High)
Risks_Issues_Dependencies | ExposureScore | Risk exposure (prob*impact weight)
Risks_Issues_Dependencies | Status | Open/Mitigated/Closed/Transferred/Accepted
Risks_Issues_Dependencies | TargetDate | Target resolve date
Risks_Issues_Dependencies | Linkage | Related milestone/dependency
Operational_KPIs | WeekStart | Week start date (Monday)
Operational_KPIs | KPI | KPI name
Operational_KPIs | PlannedValue | Planned value
Operational_KPIs | ActualValue | Actual value
Operational_KPIs | Unit | Unit of measure
Operational_KPIs | Notes | Notes