## Project_Overview
ProjectID | ProjectName | DatasetSet | ProjectTheme | Sponsor | ProjectManager | Portfolio | Domain | DeliveryMethod | StartDate | EndDate | CurrentPhase | HealthRAG | Complexity | RiskProfile | Maturity | Description
PRJ-A-005 | Spirited Away IDP | SetA | Studio Ghibli | Zeniba | Chihiro's Mother | Digital Delivery | IDP | Waterfall | 2025-08-02 | 2026-06-20 | Build | Green | High | Low | Emerging | Spirited Away IDP delivering IDP capabilities using Waterfall methods within the Studio Ghibli universe.

## Resources
ResourceID | ResourceName | Role | SkillTier | Location | CostRate_USD_per_hour | BillRate_USD_per_hour | UtilizationTarget_pct | AllocationStart | AllocationEnd
R-A-001 | Boh | QA Engineer | Mid | Studio Ghibli – Remote | 72.56 | 115.96 | 84.9 | 2025-09-16 | 2025-10-21
R-A-002 | Chihiro's Father | Architect | Principal | Studio Ghibli – Remote | 187.01 | 267.71 | 83.8 | 2025-08-21 | 2026-05-16
R-A-003 | Kamaji | Developer | Senior | Studio Ghibli – Remote | 99.85 | 125.45 | 87.6 | 2026-04-30 | 2025-11-21
R-A-004 | Boh (3) | Project Manager | Mid | Studio Ghibli – Remote | 100.25 | 158.41 | 86.9 | 2026-01-25 | 2026-01-22
R-A-005 | Chihiro Ogino | Business Analyst | Mid | Studio Ghibli – Remote | 99.18 | 150.25 | 80.7 | 2025-08-25 | 2026-01-15
R-A-006 | Yubaba | Data Engineer | Principal | Studio Ghibli – Remote | 136.42 | 202.7 | 88.9 | 2025-10-09 | 2026-02-07
R-A-007 | Yubaba (6) | Data Engineer | Principal | Studio Ghibli – Remote | 152.51 | 201.95 | 80.2 | 2025-11-24 | 2025-10-22
R-A-008 | Zeniba | Developer | Junior | Studio Ghibli – Remote | 71.75 | 105.98 | 83.7 | 2025-08-21 | 2026-02-24
R-A-009 | Lin | DevOps Engineer | Junior | Studio Ghibli – Remote | 117.91 | 175.76 | 85.9 | 2025-08-26 | 2025-10-10
R-A-010 | Boh (9) | Architect | Principal | Studio Ghibli – Remote | 131.78 | 205.63 | 84.4 | 2025-10-04 | 2026-05-23
R-A-011 | Chihiro's Mother | Developer | Junior | Studio Ghibli – Remote | 126.15 | 169.35 | 83 | 2025-09-22 | 2026-05-09
R-A-012 | No-Face | Developer | Junior | Studio Ghibli – Remote | 118.45 | 155.37 | 85.1 | 2025-10-01 | 2026-01-07
R-A-013 | Yubaba (12) | Business Analyst | Mid | Studio Ghibli – Remote | 85.31 | 114.26 | 87.8 | 2026-04-26 | 2025-11-27
R-A-014 | Lin (13) | Developer | Principal | Studio Ghibli – Remote | 102.78 | 135.89 | 89.1 | 2026-04-05 | 2026-02-01
R-A-015 | Yubaba (14) | Developer | Junior | Studio Ghibli – Remote | 71.02 | 91.62 | 88.4 | 2026-04-11 | 2025-10-31
R-A-016 | Haku | Data Scientist | Senior | Studio Ghibli – Remote | 125.25 | 197.35 | 86.4 | 2026-03-23 | 2026-01-14
R-A-017 | No-Face (16) | Developer | Junior | Studio Ghibli – Remote | 74.01 | 119.6 | 88.5 | 2026-02-02 | 2026-01-23
R-A-018 | Lin (17) | QA Engineer | Junior | Studio Ghibli – Remote | 66.95 | 109.33 | 80.1 | 2025-10-11 | 2025-11-11
R-A-019 | Yubaba (18) | Developer | Senior | Studio Ghibli – Remote | 141.56 | 237.79 | 88.8 | 2025-09-18 | 2026-02-22
R-A-020 | Lin (19) | Data Engineer | Principal | Studio Ghibli – Remote | 112.8 | 161.34 | 82.7 | 2026-02-15 | 2026-04-17
R-A-021 | Chihiro Ogino (20) | Data Engineer | Junior | Studio Ghibli – Remote | 145.42 | 233.92 | 81.3 | 2025-09-01 | 2025-11-05
R-A-022 | Chihiro Ogino (21) | Business Analyst | Principal | Studio Ghibli – Remote | 125.56 | 184.22 | 81.8 | 2026-02-12 | 2026-02-15

## Capacity_Effort
Month | ResourceID | Role | CapacityHours | PlannedHours | ActualHours | VarianceHours | Utilization_pct
2025-08-01 | R-A-002 | Architect | 56 | 47.5 | 51.1 | 3.6 | 91.2
2025-08-01 | R-A-005 | Business Analyst | 40 | 33 | 32.9 | -0.1 | 82.3
2025-08-01 | R-A-008 | Developer | 56 | 46.8 | 46.3 | -0.6 | 82.6
2025-08-01 | R-A-009 | DevOps Engineer | 32 | 26.3 | 23.7 | -2.6 | 74.1
2025-09-01 | R-A-001 | QA Engineer | 88 | 77.5 | 81.2 | 3.8 | 92.3
2025-09-01 | R-A-002 | Architect | 176 | 150.8 | 164.5 | 13.7 | 93.5
2025-09-01 | R-A-005 | Business Analyst | 176 | 147.3 | 152.9 | 5.5 | 86.9
2025-09-01 | R-A-008 | Developer | 176 | 149.1 | 155.8 | 6.8 | 88.5
2025-09-01 | R-A-009 | DevOps Engineer | 176 | 150.9 | 155.2 | 4.3 | 88.2
2025-09-01 | R-A-011 | Developer | 56 | 44.8 | 48.4 | 3.5 | 86.4
2025-09-01 | R-A-019 | Developer | 72 | 64.7
2025-09-01 | R-A-021 | Data Engineer | 176 | 149.3 | 148.4 | -0.9 | 84.3
2025-10-01 | R-A-001 | QA Engineer | 120 | 101.8 | 107 | 5.1 | 89.1
2025-10-01 | R-A-002 | Architect | 184 | 151.4 | 144.7 | -6.7 | 78.6
2025-10-01 | R-A-005 | Business Analyst | 184 | 148.6 | 145 | -3.6 | 78.8
2025-10-01 | R-A-006 | Data Engineer | 136 | 124.7 | 123.3 | -1.4 | 90.7
2025-10-01 | R-A-008 | Developer | 184 | 155.1 | 155.1 | 0 | 84.3
2025-10-01 | R-A-009 | DevOps Engineer | 64 | 54 | 56.6 | 2.6 | 88.5
2025-10-01 | R-A-010 | Architect | 160 | 128.5 | 116.6 | -11.9 | 72.9
2025-10-01 | R-A-011 | Developer | 184 | 153.5 | 162.4 | 9 | 88.3
2025-10-01 | R-A-012 | Developer | 184 | 163.8 | 176.6 | 12.8 | 96
2025-10-01 | R-A-018 | QA Engineer | 120 | 96.7 | 95.9 | -0.8 | 79.9
2025-10-01 | R-A-019 | Developer | 184 | 160.8 | 171 | 10.2 | 92.9
2025-10-01 | R-A-021 | Data Engineer | 184 | 154.7 | 163 | 8.3 | 88.6
2025-11-01 | R-A-002 | Architect | 160 | 135.4 | 131.7 | -3.7 | 82.3
2025-11-01 | R-A-005 | Business Analyst | 160 | 128.5 | 132.6 | 4.1 | 82.9
2025-11-01 | R-A-006 | Data Engineer | 160 | 135.2 | 138.8 | 3.6 | 86.7
2025-11-01 | R-A-008 | Developer | 160 | 137.9 | 134.5 | -3.5 | 84
2025-11-01 | R-A-010 | Architect | 160 | 129.7 | 129.5 | -0.2 | 81
2025-11-01 | R-A-011 | Developer | 160 | 137.1 | 134.6 | -2.5 | 84.1
2025-11-01 | R-A-012 | Developer | 160 | 132.8 | 122.7 | -10.1 | 76.7
2025-11-01 | R-A-018 | QA Engineer | 56 | 46.4 | 49.4 | 3 | 88.3
2025-11-01 | R-A-019 | Developer | 160 | 137.7 | 144.8 | 7.1 | 90.5
2025-11-01 | R-A-021 | Data Engineer | 24 | 18.6 | 19.3 | 0.6 | 80.3
2025-12-01 | R-A-002 | Architect | 184 | 148.4 | 147.1 | -1.3 | 80
2025-12-01 | R-A-005 | Business Analyst | 184 | 149.8 | 163.7 | 13.9 | 89
2025-12-01 | R-A-006 | Data Engineer | 184 | 155.5 | 157.1 | 1.7 | 85.4
2025-12-01 | R-A-008 | Developer | 184 | 153 | 166 | 13 | 90.2
2025-12-01 | R-A-010 | Architect | 184 | 159.7 | 165.8 | 6.1 | 90.1
2025-12-01 | R-A-011 | Developer | 184 | 147.7 | 136 | -11.7 | 73.9
2025-12-01 | R-A-012 | Developer | 184 | 159.1 | 153.4 | -5.7 | 83.4
2025-12-01 | R-A-019 | Developer | 184 | 169.6 | 173.3 | 3.7 | 94.2
2026-01-01 | R-A-002 | Architect | 176 | 150.3 | 147.3 | -3.1 | 83.7
2026-01-01 | R-A-005 | Business Analyst | 88 | 69.9 | 74.2 | 4.3 | 84.3
2026-01-01 | R-A-006 | Data Engineer | 176 | 150.8 | 162.5 | 11.7 | 92.3
2026-01-01 | R-A-008 | Developer | 176 | 147.5 | 148.9 | 1.4 | 84.6
2026-01-01 | R-A-010 | Architect | 176 | 145.8 | 147.3 | 1.6 | 83.7
2026-01-01 | R-A-011 | Developer | 176 | 142 | 148 | 6.1 | 84.1
2026-01-01 | R-A-012 | Developer | 40 | 34.7 | 32.1 | -2.5 | 80.3
2026-01-01 | R-A-019 | Developer | 176 | 159.6 | 149.3 | -10.3 | 84.8
2026-02-01 | R-A-002 | Architect | 160 | 134.6 | 140.3 | 5.7 | 87.7
2026-02-01 | R-A-006 | Data Engineer | 40 | 36.5 | 37.1 | 0.6 | 92.7
2026-02-01 | R-A-008 | Developer | 136 | 118.9 | 123 | 4.1 | 90.5
2026-02-01 | R-A-010 | Architect | 160 | 140.4 | 151 | 10.6 | 94.3
2026-02-01 | R-A-011 | Developer | 160 | 131.8
2026-02-01 | R-A-019 | Developer | 120 | 102.4 | 93.2 | -9.2 | 77.7
2026-02-01 | R-A-020 | Data Engineer | 80 | 63.2 | 66.8 | 3.6 | 83.5
2026-02-01 | R-A-022 | Business Analyst | 16 | 13.7 | 12.8 | -1 | 79.7
2026-03-01 | R-A-002 | Architect | 176 | 141 | 132.7 | -8.3 | 75.4
2026-03-01 | R-A-010 | Architect | 176 | 149.2 | 147.7 | -1.4 | 83.9
2026-03-01 | R-A-011 | Developer | 176 | 147.8 | 149.6 | 1.8 | 85
2026-03-01 | R-A-020 | Data Engineer | 176 | 141.5 | 138.4 | -3.1 | 78.6
2026-04-01 | R-A-002 | Architect | 176 | 147.6 | 153.4 | 5.8 | 87.2
2026-04-01 | R-A-010 | Architect | 176 | 151.4 | 147.8 | -3.6 | 84
2026-04-01 | R-A-011 | Developer | 176 | 144.9 | 150.2 | 5.4 | 85.4
2026-04-01 | R-A-020 | Data Engineer | 104 | 90 | 94.4 | 4.4 | 90.8
2026-05-01 | R-A-002 | Architect | 88 | 71.6 | 76.7 | 5.2 | 87.2
2026-05-01 | R-A-010 | Architect | 128 | 107.4 | 110.3 | 2.9 | 86.2
2026-05-01 | R-A-011 | Developer | 48 | 40.7 | 41.4 | 0.7 | 86.2

## Budget_Costs
Month | CostCategory | PlannedCost_USD | ActualCost_USD | ForecastCost_USD | CumPlanned_USD | CumActual_USD | CumForecast_USD | EV | PV | AC | CPI | SPI
2025-08-01 | Labor | 18614.85 | 18935.72 | 18169.67 | 24236.29 | 24717.57 | 25101.59 | 10600.11 | 24236.29 | 24717.57 | 0.429 | 0.437
2025-08-01 | Software | 2305.36 | 2129.85 | 2276.18 | 24236.29 | 24717.57 | 25101.59 | 10600.11 | 24236.29 | 24717.57 | 0.429 | 0.437
2025-08-01 | Infra | 1479.33 | 1343.42 | 1328.68 | 24236.29 | 24717.57 | 25101.59 | 10600.11 | 24236.29 | 24717.57 | 0.429 | 0.437
2025-08-01 | Travel | 725.92 | 693.85 | 704.29 | 24236.29 | 24717.57 | 25101.59 | 10600.11 | 24236.29 | 24717.57 | 0.429 | 0.437
2025-08-01 | Contingency | 1110.84 | 1058.46 | 1126.64 | 24236.29 | 24717.57 | 25101.59 | 10600.11 | 24236.29 | 24717.57 | 0.429 | 0.437
2025-09-01 | Labor | 113445.92 | 117300.11 | 119072.12 | 183583.53 | 188763.57 | 180341.64 | 30978.58 | 183583.53 | 188763.57 | 0.164 | 0.169
2025-09-01 | Software | 16207.21 | 16880.39 | 16045.29 | 183583.53 | 188763.57 | 180341.64 | 30978.58 | 183583.53 | 188763.57 | 0.164 | 0.169
2025-09-01 | Infra | 15829.34 | 15909.74 | 15945.98 | 183583.53 | 188763.57 | 180341.64 | 30978.58 | 183583.53 | 188763.57 | 0.164 | 0.169
2025-09-01 | Travel | 4645.21 | 5069.77 | 4852.62 | 183583.53 | 188763.57 | 180341.64 | 30978.58 | 183583.53 | 188763.57 | 0.164 | 0.169
2025-09-01 | Contingency | 9219.56 | 9257.56 | 9103.17 | 183583.53 | 188763.57 | 180341.64 | 30978.58 | 183583.53 | 188763.57 | 0.164 | 0.169
2025-10-01 | Labor | 192378.46 | 194929.39 | 196667.65 | 448250.35 | 459188.7 | 455223.71 | 86600.22 | 448250.35 | 459188.7 | 0.189 | 0.193
2025-10-01 | Software | 26613.57 | 27408.26 | 28224.41 | 448250.35 | 459188.7 | 455223.71 | 86600.22 | 448250.35 | 459188.7 | 0.189 | 0.193
2025-10-01 | Infra | 28760.61 | 26544.45 | 26728.21 | 448250.35 | 459188.7 | 455223.71 | 86600.22 | 448250.35 | 459188.7 | 0.189 | 0.193
2025-10-01 | Travel | 4471.39 | 4333.68 | 4186.82 | 448250.35 | 459188.7 | 455223.71 | 86600.22 | 448250.35 | 459188.7 | 0.189 | 0.193
2025-10-01 | Contingency | 12442.79 | 11796.63 | 12520.01 | 448250.35 | 459188.7 | 455223.71 | 86600.22 | 448250.35 | 459188.7 | 0.189 | 0.193
2025-11-01 | Labor | 141825.39 | 141556.89 | 139118.77 | 637577.71 | 647012.3 | 643918.43 | 234014.72 | 637577.71 | 647012.3 | 0.362 | 0.367
2025-11-01 | Software | 12500.1 | 12521.94 | 11990.59 | 637577.71 | 647012.3 | 643918.43 | 234014.72 | 637577.71 | 647012.3 | 0.362 | 0.367
2025-11-01 | Infra | 24029.62 | 23966.2 | 23022.2 | 637577.71 | 647012.3 | 643918.43 | 234014.72 | 637577.71 | 647012.3 | 0.362 | 0.367
2025-11-01 | Travel | 2061.43 | 1977.5 | 2105.92 | 637577.71 | 647012.3 | 643918.43 | 234014.72 | 637577.71 | 647012.3 | 0.362 | 0.367
2025-11-01 | Contingency | 8910.82 | 9180.87 | 9320.83 | 637577.71 | 647012.3 | 643918.43 | 234014.72 | 637577.71 | 647012.3 | 0.362 | 0.367
2025-12-01 | Labor | 157332.1 | 158795.12 | 151440.43 | 849546.14 | 859791.43 | 863357.7 | 514961.86 | 849546.14 | 859791.43 | 0.599 | 0.606
2025-12-01 | Software | 16255.64 | 17486.64 | 17310.41 | 849546.14 | 859791.43 | 863357.7 | 514961.86 | 849546.14 | 859791.43 | 0.599 | 0.606
2025-12-01 | Infra | 22662.11 | 23756.12 | 22207.98 | 849546.14 | 859791.43 | 863357.7 | 514961.86 | 849546.14 | 859791.43 | 0.599 | 0.606
2025-12-01 | Travel | 2899.83 | 2862.27 | 2939.69 | 849546.14 | 859791.43 | 863357.7 | 514961.86 | 849546.14 | 859791.43 | 0.599 | 0.606
2025-12-01 | Contingency | 12818.75 | 13630.83 | 12691.11 | 849546.14 | 859791.43 | 863357.7 | 514961.86 | 849546.14 | 859791.43 | 0.599 | 0.606
2026-01-01 | Labor | 130025.56 | 130776.1 | 133350.08 | 1006567.87 | 1018746.65 | 1020028.07 | 905287.27 | 1006567.87 | 1018746.65 | 0.889 | 0.899
2026-01-01 | Software | 7453.69 | 7180 | 6971.1 | 1006567.87 | 1018746.65 | 1020028.07 | 905287.27 | 1006567.87 | 1018746.65 | 0.889 | 0.899
2026-01-01 | Infra | 9972.81 | 9752.41 | 10082.6 | 1006567.87 | 1018746.65 | 1020028.07 | 905287.27 | 1006567.87 | 1018746.65 | 0.889 | 0.899
2026-01-01 | Travel | 2610.43 | 2411.16 | 2377.66 | 1006567.87 | 1018746.65 | 1020028.07 | 905287.27 | 1006567.87 | 1018746.65 | 0.889 | 0.899
2026-01-01 | Contingency | 6959.24 | 6271.53 | 6774.6 | 1006567.87 | 1018746.65 | 1020028.07 | 905287.27 | 1006567.87 | 1018746.65 | 0.889 | 0.899
2026-02-01 | Labor | 97155.31 | 98511.69 | 101392.84 | 1133989.26 | 1148290.22 | 1142684.66 | 1132086.47 | 1133989.26 | 1148290.22 | 0.986 | 0.998
2026-02-01 | Software | 9743.09 | 9073.4 | 9149.76 | 1133989.26 | 1148290.22 | 1142684.66 | 1132086.47 | 1133989.26 | 1148290.22 | 0.986 | 0.998
2026-02-01 | Infra | 9081.64 | 8572.82 | 8893.99 | 1133989.26 | 1148290.22 | 1142684.66 | 1132086.47 | 1133989.26 | 1148290.22 | 0.986 | 0.998
2026-02-01 | Travel | 3637.02 | 3816.51 | 3669.1 | 1133989.26 | 1148290.22 | 1142684.66 | 1132086.47 | 1133989.26 | 1148290.22 | 0.986 | 0.998
2026-02-01 | Contingency | 7804.32 | 8267.54 | 8395.02 | 1133989.26 | 1148290.22 | 1142684.66 | 1132086.47 | 1133989.26 | 1148290.22 | 0.986 | 0.998
2026-03-01 | Labor | 80636.16 | 78763.69 | 81432.36 | 1251749.86 | 1263180.45 | 1259566.85 | 1246451.66 | 1251749.86 | 1263180.45 | 0.987 | 0.996
2026-03-01 | Software | 11816.14 | 11565.83 | 11929.54 | 1251749.86 | 1263180.45 | 1259566.85 | 1246451.66 | 1251749.86 | 1263180.45 | 0.987 | 0.996
2026-03-01 | Infra | 14520.22 | 14658.24 | 14182.08 | 1251749.86 | 1263180.45 | 1259566.85 | 1246451.66 | 1251749.86 | 1263180.45 | 0.987 | 0.996
2026-03-01 | Travel | 2896.26 | 2655.94 | 2863.7 | 1251749.86 | 1263180.45 | 1259566.85 | 1246451.66 | 1251749.86 | 1263180.45 | 0.987 | 0.996
2026-03-01 | Contingency | 7891.83 | 7434.18 | 7884.96 | 1251749.86 | 1263180.45 | 1259566.85 | 1246451.66 | 1251749.86 | 1263180.45 | 0.987 | 0.996
2026-04-01 | Labor | 75985.3 | 77760.47 | 78373.24 | 1345907.58 | 1358549.98 | 1356833.66 | 1329936.83 | 1345907.58 | 1358549.98 | 0.979 | 0.988
2026-04-01 | Software | 4881.71 | 5360.2 | 5039.94 | 1345907.58 | 1358549.98 | 1356833.66 | 1329936.83 | 1345907.58 | 1358549.98 | 0.979 | 0.988
2026-04-01 | Infra | 5896.38 | 5953.99 | 5751.48 | 1345907.58 | 1358549.98 | 1356833.66 | 1329936.83 | 1345907.58 | 1358549.98 | 0.979 | 0.988
2026-04-01 | Travel | 2634.82 | 2711.06 | 2702.17 | 1345907.58 | 1358549.98 | 1356833.66 | 1329936.83 | 1345907.58 | 1358549.98 | 0.979 | 0.988
2026-04-01 | Contingency | 4759.5 | 4353.17 | 4719.61 | 1345907.58 | 1358549.98 | 1356833.66 | 1329936.83 | 1345907.58 | 1358549.98 | 0.979 | 0.988
2026-05-01 | Labor | 32677.39 | 34101.61 | 35069.9 | 1389043.25 | 1402493.15 | 1401149.24 | 1389043.25 | 1389043.25 | 1402493.15 | 0.99 | 1
2026-05-01 | Software | 2800.9 | 2909.28 | 2770.96 | 1389043.25 | 1402493.15 | 1401149.24 | 1389043.25 | 1389043.25 | 1402493.15 | 0.99 | 1
2026-05-01 | Infra | 4924.3 | 4581.96 | 4630.75 | 1389043.25 | 1402493.15 | 1401149.24 | 1389043.25 | 1389043.25 | 1402493.15 | 0.99 | 1
2026-05-01 | Travel | 633.33 | 641.8 | 656.65 | 1389043.25 | 1402493.15 | 1401149.24 | 1389043.25 | 1389043.25 | 1402493.15 | 0.99 | 1
2026-05-01 | Contingency | 2099.75 | 2228.96 | 2223.48 | 1389043.25 | 1402493.15 | 1401149.24 | 1389043.25 | 1389043.25 | 1402493.15 | 0.99 | 1
2026-06-01 | Labor | 0 | 0 | 0 | 1389043.25 | 1402493.15 | 1401149.24 | 1389043.25 | 1389043.25 | 1402493.15 | 0.99 | 1
2026-06-01 | Software | 0 | 0 | 0 | 1389043.25 | 1402493.15 | 1401149.24 | 1389043.25 | 1389043.25 | 1402493.15 | 0.99 | 1
2026-06-01 | Infra | 0 | 0 | 0 | 1389043.25 | 1402493.15 | 1401149.24 | 1389043.25 | 1389043.25 | 1402493.15 | 0.99 | 1
2026-06-01 | Travel | 0 | 0 | 0 | 1389043.25 | 1402493.15 | 1401149.24 | 1389043.25 | 1389043.25 | 1402493.15 | 0.99 | 1
2026-06-01 | Contingency | 0 | 0 | 0 | 1389043.25 | 1402493.15 | 1401149.24 | 1389043.25 | 1389043.25 | 1402493.15 | 0.99 | 1

## Milestones
MilestoneID | MilestoneName | PlannedDate | ActualDate | Status | SlippageDays | Owner | Critical
MS-001 | Hypercare Complete | 2025-08-20 | 2025-08-20 | Completed | 0 | Yubaba (12) | TRUE
MS-002 | Security Assessment | 2025-09-08 | 2025-09-16 | Completed | 8 | Boh (9) | TRUE
MS-003 | Training Complete | 2025-09-27 | 2025-09-28 | Completed | 1 | No-Face | FALSE
MS-004 | Hypercare Complete | 2025-10-16 | 2025-10-23 | Completed | 7 | Lin (19) | FALSE
MS-005 | Performance Test | 2025-11-04 | 2025-11-06 | Completed | 2 | Yubaba | TRUE
MS-006 | Project Kickoff | 2025-11-23 | 2025-11-20 | Completed | -3 | Haku | FALSE
MS-007 | System Integration | 2025-12-12 | 2025-12-14 | Completed | 2 | Zeniba | TRUE
MS-008 | Hypercare Complete | 2025-12-31 | 2026-01-05 | Completed | 5 | Yubaba (6) | FALSE
MS-009 | Project Kickoff | 2026-01-19 | 2026-01-21 | Completed | 2 | Yubaba (14) | FALSE
MS-010 | Security Assessment | 2026-02-07 | 2026-02-07 | Not Started | 0 | Boh (3) | FALSE
MS-011 | Performance Test | 2026-02-26 | 2026-02-25 | Not Started | -1 | Lin | FALSE
MS-012 | Training Complete | 2026-03-17 | 2026-03-22 | Not Started | 5 | Yubaba (12) | FALSE
MS-013 | Design Complete | 2026-04-05 | 2026-04-01 | Not Started | -4 | No-Face (16) | FALSE
MS-014 | UAT Complete | 2026-04-24 | 2026-04-24 | Not Started | 0 | No-Face | FALSE
MS-015 | UAT Complete | 2026-05-13 | 2026-05-08 | Not Started | -5 | No-Face (16) | FALSE
MS-016 | Design Complete | 2026-06-01 | 2026-05-28 | Not Started | -4 | No-Face (16) | FALSE

## Risks_Issues_Dependencies
RID_ID | Type | Title | Description | Owner | ImpactArea | Probability_pct | Impact | Severity | ExposureScore | Status | TargetDate | Linkage
RID-001 | Risk | Risk #1 | Synthetic risk description for test purposes. | No-Face | Quality | 34 | Medium |  | 68 | Closed | 2026-03-09 | MS-001
RID-002 | Issue | Issue #2 | Synthetic issue description for test purposes. | Haku | Cost |  | Low | Low |  | Open | 2026-03-07 | MS-001
RID-003 | Issue | Issue #3 | Synthetic issue description for test purposes. | Yubaba | Schedule |  | Low | Medium |  | Open | 2026-05-29 | MS-005
RID-004 | Dependency | Dependency #4 | Synthetic dependency description for test purposes. | No-Face (16) | Scope |  | High |  |  | Mitigated | 2026-05-24 | Vendor-Contract
RID-005 | Risk | Risk #5 | Synthetic risk description for test purposes. | Lin (19) | Cost | 26 | High |  | 78 | Closed | 2025-11-29 | Data-Center
RID-006 | Issue | Issue #6 | Synthetic issue description for test purposes. | Yubaba | Quality |  | Medium | Medium |  | Closed | 2025-11-02 | Vendor-Contract
RID-007 | Issue | Issue #7 | Synthetic issue description for test purposes. | Kamaji | People |  | Low | Low |  | Open | 2025-10-03 | Data-Center
RID-008 | Issue | Issue #8 | Synthetic issue description for test purposes. | Chihiro Ogino | People |  | Medium | Low |  | Mitigated | 2026-06-19 | Data-Center
RID-009 | Issue | Issue #9 | Synthetic issue description for test purposes. | Kamaji | Security |  | Medium | Low |  | Mitigated | 2026-06-13 | MS-001
RID-010 | Issue | Issue #10 | Synthetic issue description for test purposes. | No-Face (16) | Quality |  | Medium | High |  | Mitigated | 2026-05-07 | External-API
RID-011 | Risk | Risk #11 | Synthetic risk description for test purposes. | Yubaba (18) | Schedule | 66 | Low |  | 66 | Transferred | 2025-12-06 | MS-001
RID-012 | Issue | Issue #12 | Synthetic issue description for test purposes. | Lin (17) | People |  | Medium | Low |  | Mitigated | 2025-08-12 | MS-001

## Operational_KPIs
WeekStart | KPI | PlannedValue | ActualValue | Unit | Notes
2025-07-28 | Build Velocity | 20.29 | 20.91 | points
2025-07-28 | Defect Leakage | 8.88 | 6.68 | defects
2025-07-28 | Cycle Time | 4.81 | 3.74 | days
2025-07-28 | MTTR | 9.21 | 7.16 | hours
2025-08-04 | Build Velocity | 54.2 | 53.37 | points
2025-08-04 | Defect Leakage | 5.66 | 4.08 | defects
2025-08-04 | Cycle Time | 6.4 | 6.9 | days
2025-08-04 | MTTR | 7.31 | 8.39 | hours
2025-08-11 | Build Velocity | 39.3 | 38.28 | points
2025-08-11 | Defect Leakage | 7.55 | 5.31 | defects
2025-08-11 | Cycle Time | 4.53 | 3.95 | days
2025-08-11 | MTTR | 9.64 | 10.75 | hours
2025-08-18 | Build Velocity | 54.2 | 55.93 | points
2025-08-18 | Defect Leakage | 9.48 | 8.13 | defects
2025-08-18 | Cycle Time | 6.5 | 5.07 | days
2025-08-18 | MTTR | 5.72 | 5.03 | hours
2025-08-25 | Build Velocity | 33.54 | 33.88 | points
2025-08-25 | Defect Leakage | 8.97 | 9.56 | defects
2025-08-25 | Cycle Time | 3.8 | 4.5 | days
2025-08-25 | MTTR | 4.04 | 2.68 | hours
2025-09-01 | Build Velocity | 25.81 | 28.01 | points
2025-09-01 | Defect Leakage | 6.35 | 3.5 | defects
2025-09-01 | Cycle Time | 4.11 | 3.04 | days
2025-09-01 | MTTR | 4.3 | 3.74 | hours
2025-09-08 | Build Velocity | 59.38 | 60.73 | points
2025-09-08 | Defect Leakage | 7.21 | 7.71 | defects
2025-09-08 | Cycle Time | 5.99 | 7.02 | days
2025-09-08 | MTTR | 10.56 | 11.07 | hours
2025-09-15 | Build Velocity | 37.56 | 35.32 | points
2025-09-15 | Defect Leakage | 8.57 | 9.8 | defects
2025-09-15 | Cycle Time | 4.43 | 3.18 | days
2025-09-15 | MTTR | 8.8 | 8.45 | hours
2025-09-22 | Build Velocity | 29.27 | 27.33 | points
2025-09-22 | Defect Leakage | 2.36 | 1.63 | defects
2025-09-22 | Cycle Time | 3 | 2.34 | days
2025-09-22 | MTTR | 11.97 | 13.72 | hours
2025-09-29 | Build Velocity | 34.13 | 33.41 | points
2025-09-29 | Defect Leakage | 7.86 | 7.19 | defects
2025-09-29 | Cycle Time | 6.68 | 4.91 | days
2025-09-29 | MTTR | 4.72 | 3.77 | hours
2025-10-06 | Build Velocity | 53.19 | 57.61 | points
2025-10-06 | Defect Leakage | 5.48 | 6.96 | defects
2025-10-06 | Cycle Time | 4.38 | 4.4 | days
2025-10-06 | MTTR | 5.56 | 6.95 | hours
2025-10-13 | Build Velocity | 43 | 40.94 | points
2025-10-13 | Defect Leakage | 6.07 | 3.55 | defects
2025-10-13 | Cycle Time | 3.36 | 2.85 | days
2025-10-13 | MTTR | 11.58 | 13.45 | hours
2025-10-20 | Build Velocity | 58.27 | 62.65 | points
2025-10-20 | Defect Leakage | 10.13 | 9.73 | defects
2025-10-20 | Cycle Time | 6.47 | 7.66 | days
2025-10-20 | MTTR | 8.51 | 9.69 | hours
2025-10-27 | Build Velocity | 50.3 | 54.94 | points
2025-10-27 | Defect Leakage | 6.59 | 5.72 | defects
2025-10-27 | Cycle Time | 5.93 | 4.24 | days
2025-10-27 | MTTR | 4.93 | 3.19 | hours
2025-11-03 | Build Velocity | 45.35 | 49.83 | points
2025-11-03 | Defect Leakage | 8.77 | 6 | defects
2025-11-03 | Cycle Time | 4.58 | 5.39 | days
2025-11-03 | MTTR | 8.13 | 4.93 | hours
2025-11-10 | Build Velocity | 53.29 | 50.6 | points
2025-11-10 | Defect Leakage | 2.93 | 3.04 | defects
2025-11-10 | Cycle Time | 7.11 | 5.24 | days
2025-11-10 | MTTR | 11.45 | 10.69 | hours
2025-11-17 | Build Velocity | 34.14 | 36.83 | points
2025-11-17 | Defect Leakage | 4.69 | 5.9 | defects
2025-11-17 | Cycle Time | 6.42 | 7.41 | days
2025-11-17 | MTTR | 7.99 | 5.91 | hours
2025-11-24 | Build Velocity | 49.42 | 53.1 | points
2025-11-24 | Defect Leakage | 4.07 | 2.69 | defects
2025-11-24 | Cycle Time | 4.25 | 4.29 | days
2025-11-24 | MTTR | 5.25 | 3.54 | hours
2025-12-01 | Build Velocity | 56.81 | 58.81 | points
2025-12-01 | Defect Leakage | 8.63 | 8.56 | defects
2025-12-01 | Cycle Time | 6.82 | 6.62 | days
2025-12-01 | MTTR | 4.34 | 4.07 | hours
2025-12-08 | Build Velocity | 44.83 | 44.76 | points
2025-12-08 | Defect Leakage | 11.85 | 14.43 | defects
2025-12-08 | Cycle Time | 7.34 | 6.94 | days
2025-12-08 | MTTR | 11.88 | 14.74 | hours
2025-12-15 | Build Velocity | 31.21 | 29.48 | points
2025-12-15 | Defect Leakage | 7.77 | 4.22 | defects
2025-12-15 | Cycle Time | 7 | 6.57 | days
2025-12-15 | MTTR | 8.33 | 7.92 | hours
2025-12-22 | Build Velocity | 35.75 | 37.08 | points
2025-12-22 | Defect Leakage | 3.75 | 4.8 | defects
2025-12-22 | Cycle Time | 6.49 | 6.04 | days
2025-12-22 | MTTR | 9.51 | 5.79 | hours
2025-12-29 | Build Velocity | 28.43 | 28.89 | points
2025-12-29 | Defect Leakage | 5.25 | 5.2 | defects
2025-12-29 | Cycle Time | 4.3 | 4.19 | days
2025-12-29 | MTTR | 5.9 | 5.48 | hours
2026-01-05 | Build Velocity | 44.52 | 43.33 | points
2026-01-05 | Defect Leakage | 6.99 | 4.67 | defects
2026-01-05 | Cycle Time | 6.5 | 5.76 | days
2026-01-05 | MTTR | 10.83 | 8.62 | hours
2026-01-12 | Build Velocity | 27.2 | 25.19 | points
2026-01-12 | Defect Leakage | 7.76 | 5.3 | defects
2026-01-12 | Cycle Time | 3.5 | 2.92 | days
2026-01-12 | MTTR | 5.89 | 5.31 | hours
2026-01-19 | Build Velocity | 35.24 | 32.74 | points
2026-01-19 | Defect Leakage | 11.59 | 7.18 | defects
2026-01-19 | Cycle Time | 7.03 | 5.54 | days
2026-01-19 | MTTR | 8 | 10.37 | hours
2026-01-26 | Build Velocity | 53.98 | 54.16 | points
2026-01-26 | Defect Leakage | 9.21 | 10.39 | defects
2026-01-26 | Cycle Time | 4.5 | 4.41 | days
2026-01-26 | MTTR | 8.54 | 7.51 | hours
2026-02-02 | Build Velocity | 47.62 | 43.43 | points
2026-02-02 | Defect Leakage | 10.14 | 8.93 | defects
2026-02-02 | Cycle Time | 6.15 | 5.69 | days
2026-02-02 | MTTR | 6.68 | 5.69 | hours
2026-02-09 | Build Velocity | 42.41 | 46.08 | points
2026-02-09 | Defect Leakage | 4.58 | 2.36 | defects
2026-02-09 | Cycle Time | 3.61 | 4.09 | days
2026-02-09 | MTTR | 11.7 | 8.65 | hours
2026-02-16 | Build Velocity | 43.04 | 44.32 | points
2026-02-16 | Defect Leakage | 3.75 | 4.21 | defects
2026-02-16 | Cycle Time | 4.78 | 4.95 | days
2026-02-16 | MTTR | 7.9 | 8.81 | hours
2026-02-23 | Build Velocity | 55.59 | 54.26 | points
2026-02-23 | Defect Leakage | 4.87 | 4.89 | defects
2026-02-23 | Cycle Time | 3.72 | 2.92 | days
2026-02-23 | MTTR | 10.46 | 8.75 | hours
2026-03-02 | Build Velocity | 45.25 | 45.9 | points
2026-03-02 | Defect Leakage | 10.49 | 5.84 | defects
2026-03-02 | Cycle Time | 3.81 | 3.1 | days
2026-03-02 | MTTR | 6.54 | 5.25 | hours
2026-03-09 | Build Velocity | 30.7 | 31.59 | points
2026-03-09 | Defect Leakage | 4.71 | 4.03 | defects
2026-03-09 | Cycle Time | 7.31 | 6.45 | days
2026-03-09 | MTTR | 8.7 | 11.09 | hours
2026-03-16 | Build Velocity | 36.56 | 34.25 | points
2026-03-16 | Defect Leakage | 2.23 | 2.41 | defects
2026-03-16 | Cycle Time | 6.31 | 7.38 | days
2026-03-16 | MTTR | 9.61 | 6.3 | hours
2026-03-23 | Build Velocity | 26.68 | 24.56 | points
2026-03-23 | Defect Leakage | 2.64 | 3.17 | defects
2026-03-23 | Cycle Time | 5.74 | 4.1 | days
2026-03-23 | MTTR | 7.18 | 8.15 | hours
2026-03-30 | Build Velocity | 23.33 | 22.22 | points
2026-03-30 | Defect Leakage | 3.55 | 3.64 | defects
2026-03-30 | Cycle Time | 7.43 | 6.35 | days
2026-03-30 | MTTR | 5.98 | 4.78 | hours
2026-04-06 | Build Velocity | 45.06 | 41.74 | points
2026-04-06 | Defect Leakage | 10.39 | 5.43 | defects
2026-04-06 | Cycle Time | 6.32 | 7.14 | days
2026-04-06 | MTTR | 6.6 | 6.16 | hours
2026-04-13 | Build Velocity | 59 | 59.48 | points
2026-04-13 | Defect Leakage | 4.72 | 4.04 | defects
2026-04-13 | Cycle Time | 7.85 | 8.23 | days
2026-04-13 | MTTR | 5.42 | 5.52 | hours
2026-04-20 | Build Velocity | 45.24 | 46.47 | points
2026-04-20 | Defect Leakage | 7.64 | 7.02 | defects
2026-04-20 | Cycle Time | 6.2 | 5.3 | days
2026-04-20 | MTTR | 6.78 | 6.63 | hours
2026-04-27 | Build Velocity | 52.19 | 51.58 | points
2026-04-27 | Defect Leakage | 5.66 | 4 | defects
2026-04-27 | Cycle Time | 4.52 | 3.16 | days
2026-04-27 | MTTR | 10.52 | 12.56 | hours
2026-05-04 | Build Velocity | 33.76 | 33.55 | points
2026-05-04 | Defect Leakage | 2.08 | 2.58 | defects
2026-05-04 | Cycle Time | 7.73 | 7.26 | days
2026-05-04 | MTTR | 4.07 | 3.67 | hours
2026-05-11 | Build Velocity | 31.72 | 30.01 | points
2026-05-11 | Defect Leakage | 2.07 | 1.66 | defects
2026-05-11 | Cycle Time | 5.06 | 4.96 | days
2026-05-11 | MTTR | 7.16 | 5.11 | hours
2026-05-18 | Build Velocity | 49.48 | 48.39 | points
2026-05-18 | Defect Leakage | 5.78 | 4.11 | defects
2026-05-18 | Cycle Time | 5.11 | 4.19 | days
2026-05-18 | MTTR | 10.12 | 12.51 | hours
2026-05-25 | Build Velocity | 52.3 | 54.23 | points
2026-05-25 | Defect Leakage | 4.85 | 5.3 | defects
2026-05-25 | Cycle Time | 7.04 | 6.39 | days
2026-05-25 | MTTR | 10.83 | 7.88 | hours
2026-06-01 | Build Velocity | 31.58 | 32.45 | points
2026-06-01 | Defect Leakage | 8.18 | 5.87 | defects
2026-06-01 | Cycle Time | 6.11 | 4.85 | days
2026-06-01 | MTTR | 4.16 | 2.64 | hours
2026-06-08 | Build Velocity | 41.4 | 38.8 | points
2026-06-08 | Defect Leakage | 3.02 | 2.16 | defects
2026-06-08 | Cycle Time | 6.58 | 6.99 | days
2026-06-08 | MTTR | 5.86 | 4.14 | hours
2026-06-15 | Build Velocity | 39.74 | 38.49 | points
2026-06-15 | Defect Leakage | 5.12 | 5.83 | defects
2026-06-15 | Cycle Time | 7.99 | 7.45 | days
2026-06-15 | MTTR | 10.33 | 8.59 | hours

## Data_Dictionary
Sheet | Column | Description
Project_Overview | ProjectID | Global unique project ID
Project_Overview | ProjectName | Fictional project name
Project_Overview | DatasetSet | SetA/SetB/SetC
Project_Overview | ProjectTheme | Fictional universe label
Project_Overview | Sponsor | Fictional sponsor
Project_Overview | ProjectManager | Fictional PM
Project_Overview | Portfolio | Portfolio grouping
Project_Overview | Domain | Solution domain
Project_Overview | DeliveryMethod | Agile/Hybrid/Waterfall
Project_Overview | StartDate | Planned start date
Project_Overview | EndDate | Planned end date
Project_Overview | CurrentPhase | Current phase at time of generation
Project_Overview | HealthRAG | Red/Amber/Green overall health
Project_Overview | Complexity | Low/Medium/High
Project_Overview | RiskProfile | Low/Medium/High
Project_Overview | Maturity | Emerging/Defined/Optimized
Project_Overview | Description | Short description
Resources | ResourceID | Unique resource key
Resources | ResourceName | Fictional name
Resources | Role | Role on project
Resources | SkillTier | Junior/Mid/Senior/Principal
Resources | Location | Fictional/Generic location
Resources | CostRate_USD_per_hour | Internal cost rate ($/hr)
Resources | BillRate_USD_per_hour | External bill rate ($/hr)
Resources | UtilizationTarget_pct | Target utilization %
Resources | AllocationStart | Allocation start date
Resources | AllocationEnd | Allocation end date
Capacity_Effort | Month | First day of month
Capacity_Effort | ResourceID | FK to Resources
Capacity_Effort | Role | Role on project
Capacity_Effort | CapacityHours | Capacity hours in month
Capacity_Effort | PlannedHours | Planned hours
Capacity_Effort | ActualHours | Actual hours
Capacity_Effort | VarianceHours | Actual - Planned
Capacity_Effort | Utilization_pct | Actual/Capacity*100
Budget_Costs | Month | First day of month
Budget_Costs | CostCategory | Labor/Software/Infra/Travel/Contingency
Budget_Costs | PlannedCost_USD | Planned monthly cost
Budget_Costs | ActualCost_USD | Actual monthly cost
Budget_Costs | ForecastCost_USD | Forecast monthly cost
Budget_Costs | CumPlanned_USD | Cumulative planned cost
Budget_Costs | CumActual_USD | Cumulative actual cost
Budget_Costs | CumForecast_USD | Cumulative forecast cost
Budget_Costs | EV | Earned Value (cumulative)
Budget_Costs | PV | Planned Value (cumulative)
Budget_Costs | AC | Actual Cost (cumulative)
Budget_Costs | CPI | EV/AC
Budget_Costs | SPI | EV/PV
Milestones | MilestoneID | Unique milestone ID
Milestones | MilestoneName | Milestone title
Milestones | PlannedDate | Planned completion date
Milestones | ActualDate | Actual completion date (optional)
Milestones | Status | Status string
Milestones | SlippageDays | Actual - Planned (days)
Milestones | Owner | Responsible resource
Milestones | Critical | Critical path flag
Risks_Issues_Dependencies | RID_ID | Unique RID ID
Risks_Issues_Dependencies | Type | Risk/Issue/Dependency
Risks_Issues_Dependencies | Title | Short title
Risks_Issues_Dependencies | Description | Narrative description
Risks_Issues_Dependencies | Owner | Responsible resource
Risks_Issues_Dependencies | ImpactArea | Scope/Cost/Schedule/Quality/People/Security
Risks_Issues_Dependencies | Probability_pct | Probability for Risks (0-100%)
Risks_Issues_Dependencies | Impact | Impact level (Low/Medium/High)
Risks_Issues_Dependencies | Severity | Issue severity (Low/Medium/High)
Risks_Issues_Dependencies | ExposureScore | Risk exposure (prob*impact weight)
Risks_Issues_Dependencies | Status | Open/Mitigated/Closed/Transferred/Accepted
Risks_Issues_Dependencies | TargetDate | Target resolve date
Risks_Issues_Dependencies | Linkage | Related milestone/dependency
Operational_KPIs | WeekStart | Week start date (Monday)
Operational_KPIs | KPI | KPI name
Operational_KPIs | PlannedValue | Planned value
Operational_KPIs | ActualValue | Actual value
Operational_KPIs | Unit | Unit of measure
Operational_KPIs | Notes | Notes